## Slide 1: Case Assignment #3
The “We Have a Problem” Project
  Due 11/9/12
Scenario
  Last year your company committed to a very challenging project because your best engineers “guaranteed” they could handle the challenges and deliver the final product on time
3-month status report
  The engineers report that all is going well
  Accounting reports that the project is on budget
9-month status report
  The customer is on the phone asking for the finished product
  Accounting reports the entire budget has been expended
  The engineers report they are not ready and will need 6 more months (accounting reports this will cost an extra $600k)
  They again guarantee success stating that the problems were due to using unfamiliar, complex technologies

## Slide 2: Case Assignment #3 (cont.)
Analyze the state of the project
  Provide a description of what YOU believe went wrong
  Support with an earned value analysis graph
    EVM graph plotting the PV, EV and AC lines
    Plot points for 0, 3, and 9 months
    Plot EV and AC points for 100% completion
  Recommend and justify next steps
    Calculate SV, CV, SPI and CPI for the 3 and 9 month reporting periods
    Recommend a plan for completing the project in 12 months
    Document the changes you recommend and estimate the new budget
Analyze the state of the company
  Who should be fired?
  Document a process improvement plan stating specific changes you would implement so that future projects will be more likely to succeed