## Slide 1: Project Management for ITM ITM 471/571
Dennis Hood
School of Applied Technology
Fall ‘14

## Slide 2
Week 11
Process Improvement and PM Models

## Slide 3: Lesson Overview
Process Improvement and PM Models
Reading: Chapter 12
Objectives
  Examine the topic of process improvement as it pertains to the project management process
  Discuss approaches for improving the PM process
  Analyze the role of metrics in improving the PM process
  Compare and contrast different PM models

## Slide 4
Process Improvement

## Slide 5: Improving a Process
Processes are inherently improvable
  The more you examine a process the more imperfections you’ll spot
  Just when you think you’ve squeezed out all of the inefficiencies, along comes a technology innovation!
Improvements should be strategic
  Make decisions based on benefits and costs
Change is hard so be gentle

## Slide 6: Motivation
Change is a constant threat
  IT managers rely on the unreliable – people and tools
  People use tools in the context of a process to (hopefully) create value
  Processes are often more manageable and stable
Knowledge is power
  Understanding the “as-is” allows us to move methodically (and strategically) toward the “to-be”
  Decreasing inefficiency and increasing productivity results in greater profit

## Slide 7: The Physics of Process Flow
Bottlenecks
  Where is the flow most restricted?
Friction
  Is the flow inhibited? (bureaucracy, etc.)
Inertia and momentum
  A process at rest tends to stay at rest
Conductivity and insulation
  Do motivators exist to encourage positive flow?
  Is the process isolated from “distractions” and “noise”?

## Slide 8: Variability of Process
Variety
  The spice of life
  Death to a production line
Managing variability requires knowledge of
  The desired output
  The degree of tolerance
Reducing variability (increasing predictability) takes effort ($)
Side benefits can be significant

## Slide 9: Goal-based Improvement
Focus on improvement
  A focal point is essential to achieving significant, sustainable improvement
Don’t try to get it all in one swing
  If the end of the tunnel is so far away that we can’t see the light, then we need interim goals
  Success is a journey – just keep heading in the right direction

## Slide 10: The Role of Feedback
Get connected
Timing is everything
Be SMART
Thresholds are necessary to prevent overreaction
Proactivity vs. reactivity
  Is it process improvement or quality control?

## Slide 11: Quality Focus Thru the Years
The assembly line
TQM
ISO 9000
Deming
Baldridge
CMM
Six Sigma

## Slide 12: Six Sigma: Methodology or Religion
Process change, Six Sigma style
  Management
  Improvement
  Redesign
Zen and the art of process improvement
  If you look closely enough, you will see variation
  If you focus on it, will it improve?

## Slide 13: Six Sigma Mechanics
No more than 3.4 defects per million opportunities (DPMO)
Implies that
  We know (exactly) what a defect is
  We know (exactly) what an opportunity is
  We have a measurement process that
    Accurately detects any defect
    Is unobtrusive enough so as not to significantly impede productivity

## Slide 14: Statistically Speaking
Six Sigma assumes a normal distribution (bell curve) of event outcomes
99.99966% of outcomes will be within six standard deviations of the mean
  In other words, only 3.4 of every million outcomes will be outside the six standard deviation range
It only works if
  You really have a normal distribution
  You target the mean and
  You bound your acceptable range of outcomes at -/+ six standard deviations

## Slide 15: Six Sigma Projects
Define requirements
  Suppliers, Inputs, Process, Outputs, Customers (SIPOC)
  Critical-to-Quality (CTQ)
Measure existing vs. desired
  Focus on the “important” outputs that can be improved
Analyze data to identify causes
Improve the process
Control the results and maintain

## Slide 16: The Capability Maturity Model
Developed to address software project failure rates
  US Defense Department (DoD) and the Software Engineering Institute (SEI)
  Lack of maturity of process in engineering software was believed to be the leading cause of an alarming failure rate
A framework for improvement
  Five distinct levels of process maturity
  Key process areas that must be satisfied

## Slide 17: CMM’s Levels
Initial (aka ad hoc, chaotic, disorderly)
Repeatable
  Disciplined enough to repeat successes
Defined
  Defined and documented process, tailored
Managed
  Quantitatively understood and controlled
Optimizing
  Continuously improving

## Slide 18
PM Life Cycle Models

## Slide 19: PM Life Cycle Models
Linear
Incremental
Iterative
Adaptive
Extreme

## Slide 20: The Linear Model
Waterfall approach
  Scope
  Plan
  Launch
  Monitor & Control
  Close
Phase relationships are finish-to-start
Very well understood goal and solution
  “We’ve done this many times before”
Intolerant of learning / change

## Slide 21: The Incremental Model
Piecemeal version of the waterfall approach
Phased deliverables provide earlier, lesser value in increments
Learn as you go – change as necessary

## Slide 22: The Iterative Model
Iteration is used to explore, discover and learn while moving toward an acceptable level of completion
Iterations produce increasingly complete prototypes to facilitate discovery of the complete solution
Scope can be “refined” between each iteration

## Slide 23: The Adaptive Model
The future is less certain
Knowledge gained in one iteration will be used to direct the next iteration
  Just-in-time planning
The goal is convergence toward an acceptable solution
  High-risk, high-reward?
Partial solutions may be released at the discretion of the client

## Slide 24: Extreme Project Management
Rapid and very visible progress toward a yet to be determined solution to a vague and evolving problem
Capability and desire in search of a solution which in turn will search for a problem
Change is a given since the next iteration is at best loosely defined until the current iteration is assessed
Success must be thought of in different terms – knowledge gained

## Slide 25: Extreme PM Evaluated
Strengths
  Extremely engaging (creative problem solving)
  Extremely flexible
  Rapid breezing over of many possible solutions
  Facilitates getting “out of the box”
Weaknesses
  Commitment to anything but exploration is futile
  Encourages play, not work
  Drives sales and marketing crazy
  Who’s paying for this?