## Slide 1: Project Management for ITM ITM 471/571
Dennis Hood
School of Applied Technology
Fall ‘14

## Slide 2
Week 5
Risk Management

## Slide 3: Lesson Overview
Risk Management
Reading: Ch. 6
Objectives
  Explore the sources of risk and approaches for managing it
  Define risk in terms of likelihood and impact
  Analyze mitigation and contingency planning as part of project management

## Slide 4: Homework Assignment 1
You are the PM of a project which must complete on time to avoid a $500k fine
You have identified the following threats to on-time completion and estimated the likelihood of each:
  Not enough time (30%)
  Insufficient funding (20%)
  Insufficient effort (25%)

## Slide 5: Homework Assignment 1 (cont.)
Document your risk management plan
  Provide the exposure for each risk
  Provide a response plan for each risk
    Mitigation / transfer action(s)
    Estimated response cost and revised exposure
    Statement of cost vs. benefit
  Describe a plan to monitor each risk
    Metrics collection
    Contingency plan
Submit to Blackboard by 10/4/14

## Slide 6
The Risk Management Process

## Slide 7: Risk Management
Plan Risk Management
Identify Risks
Perform Qualitative Risk Analysis
Perform Quantitative Risk Analysis
Plan Risk Response
Monitor and Control Risks

## Slide 8: The Nature of Risks
Risk and opportunity go hand-in-hand
  Strategically taking risks and succeeding puts you ahead of the competition
  Risk-taking is energizing and unifying
Risk-taking expands knowledge
  Discovery comes from plunging into the unknown
Cost-Benefit is based on utility and exposure
  (Perceived) Benefit = Intrinsic Value + Actual Gain – Cost
  (Perceived) Loss = Intrinsic Impact + Actual Loss + Cost
  Expected Utility = Psuccess•Benefit - (1-Psuccess)•Loss
  Risk Exposure = Likelihood • Impact

## Slide 9: Planning
Inputs
  Scope and quality requirements
  Constraints
    Time, cost, resources, etc.
  Past history
Planning meetings and analysis
Risk management plan
  Framework for dealing with threats
  Responsibilities, general sense of impact, etc.

## Slide 10: Identify Risks: Tools and Techniques
Reflect on past projects to determine causes of past failures and near failures
Ask those being asked to commit
  Commitment leads to anxiety
  Anxiety reflects risk
Talk to the experts
SWOT analysis
  Strengths and weaknesses
  Opportunities and threats

## Slide 11: Identify Risks: Sources of Risk
Activity scheduling
  Activity dependencies and critical paths
  Time pressure
Organization and resource management
  Structure - Command, control and communication
  Human issues – team play, skills, experience, etc.
Funding
Scope creep and related changes
Ambiguous constraints, especially quality
Lack of process
New technology

## Slide 12: Risk Analysis
Qualitative
  Relatively quick initial assessment
  Fuzzy assessments of likelihood and impact at first (e.g., low, medium, high)
Quantitative
  Get to financial measure of exposure
  Likelihood is a probability
  Impact is a financial assessment
Prioritize by exposure ratings
Set aside “acceptable” risks

## Slide 13: Plan Risk Responses
Avoid
  Consider a different, risk-free approach
Transfer
  Transfer ownership to a 3rd-party
Mitigate
  Reducing the likelihood and/or impact
  May result in either transfer or avoidance
Accept
  Create a monitoring process
  Establish corrective actions

## Slide 14: Plans for Common Risks
Activity scheduling
  Insert buffers such as reviews
  Attend to the critical path
Organization and resource management
  Close communication gaps and look for cross-impacts
  Skills, experience and a good night’s sleep all matter
  Engage and involve the team
Funding
  Proactively manage the flow of cash
Scope creep
  Thoroughly analyze requirements then lock them down
  Make the users part of the process
  Establish and enforce change management procedures
Develop formal processes

## Slide 15: Dealing with Technology Risks
Technology changes frequently
  Keep projects short
  Anticipate upcoming advancements
Change leads to growth
  Establish a culture of R&D
  Reward prudent risk taking
Manage new technology insertion
  Provide adequate training
  Test drive before you commit
  Import expertise
  Participate in lessons-learned forums

## Slide 16: Cost-Benefit Analysis
Compare the cost of mitigation with the benefit (the reduced exposure)
  Exposure is a financial value
  Mitigation always costs something
  Benefit = ∆Exposure
Analyze completely
  Exposure changes with time
  Account for transferred risks

## Slide 17: Monitoring and Controlling Risks
Monitor the prioritized list of risks
Establish metrics and the associated measurement process for each risk
Determine triggers that will initiate action
Document the contingency plan for each
Recognize that monitoring is intrusive
Reassess risks frequently