## Slide 1: Project Management for ITM ITM 471/571
Dennis Hood
School of Applied Technology
Spring ‘14

## Slide 2: Homework Assignment 2
Project overview
  Develop a new software product
  Finish as soon as possible
    You must finish in 42 weeks or less to avoid a $1 million fine
    You will receive a $200k bonus for each week sooner than 42
  It would be nice if your budget was under $2.5 million
  You may need to make compromises to achieve “success”
Please see the activity details
  Durations are in weeks; Costs are in thousands of dollars
  Both the expected (“normal”) and the maximally compressed (“crash”) values are provided for each activity
  Activity dependencies are also provided with the listing of each activity’s predecessor(s)
  In addition to the given activity costs, your project will incur a $2k per week administrative overhead fee

## Slide 3: Homework 2 – Activity Details

## Slide 4: Homework 2 - Deliverable
Define “success” for this project
Draw a precedence diagram for the "normal" schedule
  show the critical path(s)
  expected project costs (indirect, direct and total)
  expected project duration
  justify any assumptions
Advise the team of their situation
  Use our compression algorithm to identify options
  Draw a project cost-duration graph showing all solutions
  Choose the “best” plan and use cost-benefit analysis to justify your selection
  SHOW ALL WORK and JUSTIFY ALL ASSUMPTIONS!
Due 10/18/14

## Slide 5
Week 7
Schedule Management

## Slide 6: Lesson Overview
Schedule Management
Reading: Ch. 9
Objectives
  Explore scheduling issues and approaches to effective schedule development
  Analyze scheduling and resource allocation techniques
  Revisit risk management with regard to scheduling decisions
  Define “Traditional Project Management”

## Slide 7: Identifying Milestones
Choose points of significant accomplishment
  Successfully achieving a milestone should be reason to celebrate for the entire team
  Milestones should be focal points for the team
Choose points of transition
  Analogous to reaching a plateau when climbing a mountain
  A place to catch your breathe, reflect on what’s been accomplished, and re-evaluate the plan before moving on
Milestones must be clearly defined and attainable
Not too many, not too few

## Slide 8: Making It Real
Apply the precedence diagram to a calendar
  Real-time means account for holidays, weekends, meetings, downtime, etc.
Assign resources to the tasks
  Match by skill set first,
  then look at availability
  Account for vacations, possible sick time, etc.
This is usually done with a GANTT Chart

## Slide 9: WBS to Network to Schedule
Evolution of analysis
  All activities from the WBS analysis must be accounted for
  All dependency relationships from the Network Diagram must be respected
  Schedules are typically depicted in Gantt chart form
Resource Allocation
  Each activity must have a logical resource allocated to it (in terms of skills and experience)
  Resources must not be over-allocated

## Slide 10: Know Your Critical Path
The critical path dictates the project’s duration
  All other paths contain float
Delays to critical activities delay the project
  Manage risk along the CP aggressively
    Dependable resources
    Milestones and quality reviews
    Strategic buffers
Compression is only possible along the CP
  Compressing a CP activity will compress the project by the same amount as long as enough float exists in the non-critical paths

## Slide 11: Critical Chain Method
Goldratt, The Goal and Critical Chain
  Theory of Constraints
  Respects both resource and technical constraints
Observations
  People pad estimates
  But people tend to use the padding
  Early completion is often not reported so the opportunity is lost
  Multitasking overhead is under estimated
  A few key resources truly drive the project and therefore bottlenecks are created around people
  People procrastinate

## Slide 12: Pressure to Compress
Reasonable sources of pressure
  Time is money
    Though not completely correlated: if the project completes sooner it will cost less
  Market windows and competition
  We all know you padded the schedule!
Unreasonable sources of pressure
  Management is trying to appease
  We have to fit the budget cycle
  We’re late!

## Slide 13: Getting it Done Sooner (or Cheaper)
Respect the scope triangle
  Reducing time usually increases cost
  Unless scope and/or quality is sacrificed
Focus on critical path activities
  You can only reduce total project duration by reducing critical path activity durations
  Remember – compression creates new CPs
Reassess risk
  Schedule compression is inherently risky
  Beware the Mythical Man Month (Brooks)

## Slide 14: Compression Options
Feasible
  Reduce scope
  Phased-delivery, throwaways and prototypes (extreme programming)
  Outsource
  Dedicated project teams
  Fast-track and crashing
Risky
  Add resources
  Schedule overtime
  Compromise quality
Wishful thinking

## Slide 15: Compression Cost-Benefit Analysis
Assuming compression is feasible (safe, respects scope triangle, etc.) we still need to assess its value
  Is the benefit of the compression worth the cost?
  Remember, crashing has its limits and is inherently risky
Project indirect costs
  Overhead that varies directly with time
  Administration, supervision, rent, etc.
  The shorter the project, the lower the indirect cost
Project direct costs
  Driven directly from activities
  Labor, equipment, subcontractors, etc.
  Can the activity be done faster? At less cost?

## Slide 16: Compression Analysis Graphs
Project Cost-Duration Graphs
  Graph the total project direct, indirect, and sum costs by time for each feasible project duration
  Identifies the optimum cost-duration point
Activity Graphs
  Examines the cost per unit time of an activity
  Activity costs assume “normal” time
  Activities can be “crashed” at a cost (scope triangle)
  Goal: crash CP activities with the smallest increase in cost per unit time

## Slide 17: Compression Algorithm
Calculate the cost to compress each activity by one unit of time (slope)
Identify the CP activities
  Compress the project by one unit of time by compressing the activity (or combination of activities) with the lowest cost (smallest slope)
    It may be necessary to compress more than one activity if there are multiple CPs
    Compress each activity by only one unit of time per iteration
Recalculate the CP
Iterate steps 2-4 until “done” compressing

## Slide 18: Resource Allocation
Resources extend from human to materials, equipment and working capital
Utilization
  Both over and under-utilization can cause problems
  Keep people engaged but leave breathing room
  Projects are more marathon than sprint
Smoothing
  Take advantage of available float
  Switch assignments if feasible
  Adjust dependencies if necessary

## Slide 19: Multiproject Scheduling
Benefits
  Improved global utilization
  Key resources provide skills and experiences to more than one project
  Increased employee engagement
Risks
  Multiple-boss problem at the project level
  Schedule changes in one project can create conflicts with another
  Project switching overhead can decrease effectiveness

## Slide 20: Managing Risk in Scheduling
Things requiring risk management
  Merges and bursts
  Critical path activities
  Heavily utilized resources
Variability is risk
  Risk accumulates with each activity
  Seems like we’re late more often than early

## Slide 21: Measuring and Reporting Status
Measure progress vs. plan
  Has the milestone been achieved?
  Has the deliverable been produced? To satisfaction?
  To what degree has the activity been completed? To satisfaction?
Document and communicate progress
  Status reports should report on activity completion
  Reporting should be sequenced to allow for effective review
  Deviations from plan must follow risk and change management plans

## Slide 22: Scheduling for Success
Allocate resources to match required skills and experience levels
Mitigate schedule risks with strategic buffers
Make the most of your milestones
  Measurable
  Attainable
  Useful
Build a schedule you can manage
  Measure and document progress
  Manage change effectively

## Slide 23: Traditional Project Management
Linear PM Life Cycle (PMLC) Model
  Dependent phases executed sequentially
  Best if
    Scope is well defined and not likely to change
    Activities are fairly routine (predictable)
    Established templates can be utilized
Incremental PMLC Model
  Dependent phases repeated in sequential order (still no feedback)
  Best if
    Interim deliverables (partial solutions) are desirable
    “Final” deliverable is not completely understood
    Some scope change is expected due to “on-the-fly” clarification
    Resources are scarce and must be allocated more dynamically