## Slide 1: Project Management for ITM ITM 471/571
Dennis Hood
School of Applied Technology
Fall ‘14

## Slide 2
Week 8
Cost Management and EVM

## Slide 3: Lesson Overview
Cost Management and Maintaining Control
Reading: Chapter 9
Objectives
  Discuss the activities required to manage project costs
  Examine methods for establishing and managing project budgets
  Discuss monitoring as a process for keeping projects on target
  Identify metrics that facilitate effective monitoring as well as methods for collecting and using them effectively
  Examine the earned value approach to monitoring projects

## Slide 4: Cost Management
Estimate costs
  Direct costs
    Labor effort over time
    Systems, tools, materials, etc.
  Indirect costs (administration, etc.)
Establish budget
  Expenditures over time
  Justification of costs
Control costs
  Establish baseline
  Measure actual and compare to plan

## Slide 5: The Cost Management Plan
Overrunning the budget is a significant project risk that must be managed aggressively
The Cost Management Plan is part of the overall Project Management Plan
  States how costs will be estimated and planned, and
  how actual expenses will be managed with respect to the plan
The following should be considered during planning:
  The required level of accuracy for cost estimates
  The units of measure for each cost driver (e.g., “per week”)
  Control Account codes to link costs to organizational units
  Control or variance thresholds for triggering contingencies
  The rules for measuring performance (e.g., EVA)
  Reporting formats and frequency – different stakeholders may have different needs/requirements
  The inclusion of indirect costs (e.g., administrative overhead)

## Slide 6: Estimating Costs
Let past experience help predict the future
  The same methods used to estimate time
Time is money – so look to duration estimates
  Estimate how much it will cost to successfully complete each activity
  The schedule usually drives the budget, but consider altering the schedule to get a better budget (e.g., materials may be cheaper if purchased sooner or later than originally scheduled)
Non-labor resources (e.g., systems, tools, etc.) cost money too
Don’t forget to pay yourself (PM activities)
Strategically allocate reserves, but don’t pad!

## Slide 7: Estimation Accuracy
Generally speaking, increasing the accuracy of an estimate will take more time and effort
  Rough Order of Magnitude (ROM) Estimate
    Usually made during project initiation
    Typically a range of +/- 50% from the actual cost
  Budget Estimate
    Usually made during project planning
    -10 to +25% from actual
  Definitive Estimate
    Refinements made during the project
Generally speaking, the more accurate an estimate is, the more valuable it will be

## Slide 8: Determining the Budget
The process of aggregating estimated costs to establish an authorized cost baseline
  How much money should the organization prepare to expend in total?
This includes contingency/reserve funds that should be set aside to recover from risks
  Contingency funds are associated with known risks
  Management reserves can be added to the budget to cover “unknown” risks such as unplanned scope changes
Cash flow analysis is necessary to ensure that required funds are available when needed

## Slide 9: Controlling Costs
Actual project performance must be monitored and controlled to ensure adherence to the plan and, if necessary, to trigger contingencies to recover from deviations
Controlling the project from a cost perspective
  Collect expenditure data
  Compare with planned cash flow (limited value)
  Incorporate “true” project progress (earned value)
  Trigger contingency if variance exceeds threshold
  Report budget status
Increases in the budget must be formally approved

## Slide 10: Monitoring Progress
Goals
  Keep the project on target (“You Are Here”)
    Implies the presence of a baseline
  Feed data to risk and change control
  Provide visibility for stakeholders
  Collect data for the knowledge base
Monitoring is inherently intrusive
  Take what is readily available
  Extract the rest carefully
  Keep the process objective and positive
Are people more productive when they are being watched?

## Slide 11: What to Measure
Progress
  How far along is the project?
  Are we hitting our milestones?
  How much is left?
Stability
  How frequently is the direction changing?
  Are we in control? Is control attainable?
Quality
  How “acceptable” are the work products?
  Do we need to “rework” anything?

## Slide 12: Earned Value Management
Combines time, cost, and work completed
  Used to determine project status
  How much value has been created to date?
  Implies the existence of a phased budget and the ability to collect actual cost and progress over time
Base metrics
  Planned Value (PV)
    estimated value of work planned to date
    PV at the target completion date equals the budget (BAC)
  Earned Value (EV)
    estimated value of work actually completed
  Actual Cost (AC)
    actual cost of the work actually completed

## Slide 13: EV Derived Metrics
Variance – difference from plan
  Cost Variance (CV) = EV - AC
  Schedule Variance (SV) = EV - PV
  Cost Performance Index (CPI) = EV / AC
  Schedule Performance Index (SPI) = EV / PV
Forecasting completion
  Estimate at Completion (EAC)
    As of now, how much do we expect the project to cost?
    At planned rate of spending vs. at actual rate of spending
  Estimate to Complete (ETC)
    Estimated remaining cost
  Variance at Completion (VAC)
  To-Complete Performance Index (TCPI)
    Rate to meet in order to stay within budget

## Slide 14: Using Earned Value Analysis
Variance analysis
  Compute the schedule and cost variances
  Positive is good, negative indicates lag relative to plan
Efficiency analysis
  Compute CPI and SPI
  <1 indicates inefficient relative to expectations

## Slide 15: Using Metrics to Improve the Process
Capability Maturity Model (CMM)
  Each level is characterized by increasing proficiency at monitoring
  Achieving a CMM level requires quantitative proof of capability
Feedback Loops
  Educate the team on what did and didn’t work
  Metrics make it objective
  Gets the team focused on areas in need of improvement and the size of the gap
Historical Data
  Along with experience, the project manager’s best friend