## Slide 1: Project Management for ITM ITM 471/571
Dennis Hood
School of Applied Technology
Fall ‘14

## Slide 2: Case Assignment #3
Scenario
  Last year your company committed to a very challenging project because your best engineers “guaranteed” they could handle the challenges and deliver the final product on time – you are the project manager
5-month status report
  The engineers report that all is going well
  Accounting reports that the project is on budget
10-month status report
  The customer is on the phone asking for the finished product
  Accounting reports the entire budget has been spent
  The engineers report they are not ready and will need 5 more months (accounting reports this will cost an extra $500k)
  They again guarantee success stating that the problems were due to using unfamiliar, complex technologies

## Slide 3: Case Assignment #3 (cont.)
Analyze the state of the project
  Draw an EVM graph
    Plot the PV, EV and AC lines
    Plot points for 0, 5, and 10 months
    Estimate EV and AC for 100% completion (show on the graph)
  Recommend and justify next steps
    Calculate SV, CV, SPI and CPI at 5 and 10 months
    Recommend changes to complete the project by month 13
Analyze the state of the company
  Who should be fired (and why)?
  Document a process improvement plan stating specific changes to make future projects more likely to succeed
Due 11/15/14 (Blackboard)

## Slide 4
Week 10
Closing Phases

## Slide 5: Lesson Overview
Auditing and Closing Projects
Reading: Chapter 8
Objectives
  Discuss activities associated with closing things – contracts, phases, projects, etc. – such as audits, lessons learned analysis, etc.
  Discuss the role of contracting and purchasing
  Examine different types on contracts and strategies for entering into them
  Analyze buy vs. build-type decision making

## Slide 6
Closing Phases

## Slide 7: Achieving Milestones
Closure
  Managing phase closure is critical to future success
  This applies to interim phases as well as the project as a whole
Analysis
  Capture metrics
  Assess state
Stakeholder management
  Record and report
  Obtain approval and move on
Keys to success
  Start with the end in mind
  Be disciplined (no cutting corners!)
  Celebrate success
  Learn

## Slide 8: Are We There Yet?
The project is done when:
  You deliver the deliverable and the customer accepts it
  The stakeholders agree to end it
  Never, it will go on forever!
  It fails (and everyone admits it)
  It’s cancelled (due to outside influences)
The ability to accurately assess the state of the project is key

## Slide 9: A Time of Reflection
Audit goals
  Identify the successes and failures
  Gain an understanding of why (root causes)
  Learn and record the knowledge
The process
  Start with objective actual vs. planned data, then supplement with testimonials
  Identify significant goods and bads
  Do the detective work to determine the true sources
  Record the lessons learned for future improvement

## Slide 10: Keys to an Effective Audit
It’s not about blame
  Chances are it was more process than person anyway
Focus on the big items
  Chances are solving them will probably correct the little ones anyway
Try to balance positives and negatives
  No project is all good or all bad
  You can learn as much from your successes
Get a good scribe

## Slide 11: Questions to Address
Did the team follow the plan?
Was the schedule appropriate? budget?
Did the PM lead effectively? manage?
Was the team cohesive and effective?
Did we have the right people? tools? training?, etc.
Was risk managed well? change?
Was communication proactive?
Were we able to do it right?

## Slide 12: Evaluating Performance
Start with teams, then look at individuals
Gather feedback from multiple sources
Be objective, fact-based, honest and just
Keep true to the accountabilities established during planning
Emphasize successes and areas in need of improvement
Reward those who made it happen

## Slide 13: Where Do We Go From Here?
Celebrate success, or at least the accomplishment of completion
Respect the team’s momentum and comfort with each other
Look for opportunities to advance individuals
Relax, reflect and refresh
Do it again - only this time do it better!

## Slide 14: Procurement Management Process
Obtaining the supplies, resources, services, etc. required by the project
  Buying from a seller
Issues
  Rules and regulations
  Negotiation and relationships
  Buy vs. build
  Useful life
Steps
  Plan - identify needs, evaluate sellers, etc.
  Conduct - negotiate and select sellers
  Administer – manage relationships, change, etc.
  Close

## Slide 15: Procurement Contracts
Contracts are binding and must therefore be respected
  It can be both shield and sword – either for or against you!
  Change management discipline is key
  The project manager should be involved in developing the contract

## Slide 16: Procurement Decisions
Determine need
Buy vs. build vs. borrow
  Risk is a cost
  Time has value
Seller selection
  The pros and cons of “preferred” vendors
  Capability, including relevant experience
  Motivation
Post-engagement responsibilities
  Ownership
  Maintenance

## Slide 17: Paperwork
Statements of work (SOWs)
Requests for proposal (RFPs)
  Also requests for bids or quotes
Purchase orders (POs)
Contracts
  Fixed price vs. Time and material vs. Cost reimbursable
  Delineation of responsibilities
  Acceptance
Nondisclosure agreements

## Slide 18: Administer Procurements
Disciplined change management
Quality assurance
Verifiable completion of scheduled work
Proactive communication
Risk monitoring supported by EVM

## Slide 19: Project Maturity Model
Organizational Project Maturity Model
  Developed by the PMI
  Modeled after SEI’s CMM
Levels of maturity
  Ad hoc – Lacks predictability
  Formal – PM standards are applied
  Institutionalization – Organization-wide
  Management – system support for portfolio management
  Optimization – Continuous improvement