## Slide 1: Project Management for ITM ITM 471/571
Dennis Hood
School of Applied Technology
Fall ‘14

## Slide 2
Week 4
Planning and WBS

## Slide 3: Lesson Overview
Planning Documents and Work Breakdown Structures
Reading: Chapter 5
Objectives
  Examine the planning process and associated documentation
  Analyze the process of defining scope
  Examine the Work Breakdown Structure (WBS) as a tool for establishing scope
  Analyze requirements verification and control

## Slide 4: The Planning Process Group
Develop Project Management Plan
Scope Management Planning
  Collect Requirements
  Define Scope
  Create WBS
Schedule and Budget Planning
Plan Quality and Develop HR Plan
Plan Communications
Risk Management Planning
Plan Procurements

## Slide 5: The Scope Management Processes
During Planning
  Collect Requirements
  Define Scope
  Create Work Breakdown Structure (WBS)
During Monitoring and Controlling
  Verify Scope
  Control Scope

## Slide 6: The Scope Statement
Describes the project’s deliverables and the work required to create them
Consists of:
  Product scope description
  Product acceptance criteria
  Project deliverables
  Project exclusions
  Project constraints
  Project assumptions

## Slide 7: Inter-related Project Parameters
What we can accomplish (scope) and how well we do it (quality) are factors of:
  How much we invest (cost)
  How long we take (calendar time)
  And how hard we work (resource effort)
A change to any of these 5 factors forces a change to at least 1 of the other 4

## Slide 8: Managing Project Priorities
Priorities determine which factors are:
  Constrained / Fixed – cannot be altered
  Enhance – should be optimized
  Accept / Tolerate – can be slackened
Factors must be negotiated to meet the objectives of the project while still maintaining the equilibrium of the scope triangle

## Slide 9: Work Decomposition
Breaking the goal into manageable pieces
Decomposition techniques
  Top-down vs. bottom-up
  Activities vs. deliverables
Stopping Rules
  Progress and completion can be measured
  Start and end events are clearly defined
  Each activity has a deliverable
  Effort can be estimated with confidence
  Required skills are well understood

## Slide 10: Work Breakdown Structures
A representation of the hierarchy of decomposed activities
  The top level represents the project’s goal
  The leaves represent the assignable work
  Intermediary levels represent “roll-ups” of related activities (phases, components, etc.)
Roll-ups
  Provide cost and effort summaries for logically-related activities

## Slide 12: Uses for the WBS
Helps analyze the project’s activities and deliverables
Helps frame the system architecture
Helps organize the project team
Helps analyze costs and establish budget
Provides a baseline for reporting status
Helps communicate work assignments and inter-dependencies

## Slide 13: Looking Ahead: Controlling Scope
Scope change may be the most significant threat to project success
  The initial effort to establish a clear understanding of scope is invaluable
  Disciplined change management must be employed to maintain control of the project
Progress will be measured in terms of activity completion
  Independent verification of completion
  Milestones