## Slide 1: Project Management for ITM ITM 471/571
Dennis Hood
School of Applied Technology
Spring ‘14

## Slide 2
Week 6
Estimation and Control

## Slide 3: Lesson Overview
Estimation
Sequencing Activities (Precedence Diagrams)
Reading: Ch. 7
Objectives
  Develop methods for sequencing project activities
  Discuss techniques for optimizing networks
  Explore critical path management and other advanced sequencing topics
  Evolve project planning from WBS analysis to calendar scheduling

## Slide 4: Where is the Storm Going to Hit?
Pressure to provide an early answer can lead to errors and certainly lowers certainty
Change is inevitable
Variability due to risk is difficult to factor in
Political pressure to provide the right answer breeds cynicism
Fear of punishment breeds padding

## Slide 5: The Benefits of Good Estimating
Estimate Defined
  A credible approximation of the effort, time and cost required to successfully complete the project determined through careful analysis
Risk Reduction
  Enables more accurate resource planning
  Reduces the likelihood of running short or running out of critical resources
  Sets realistic stakeholder expectations
Motivates Early Analysis
Facilitates Communication
Improves Plan Credibility

## Slide 6: Estimation Challenges
Uniqueness
  History is the best predictor of future results
  Discovery will provide answers that lead to more accurate estimates, but we need an estimate now!
Complexity
  Many variables to consider
  May need to view multiple perspectives
Is the project team doing the estimating?

## Slide 7: Is Estimating Part of the Project?
Estimation takes time and resources
More such investment leads to more accurate estimates
Is this effort part of the project?
  Generally, initial estimates (macro) associated with project selection are not (Project Office and experienced personnel)
  More detailed estimates (micro) necessary to build the plan are (PM and key team members)
  This is largely semantics and accounting

## Slide 8: Estimating Activity Attributes
Finalize your definition of each activity
  Resources
    Skills required, desired level of experience, etc.
    Match with available (or attainable) resources
    Systems, tools, etc.
    Compile a resource calendar
  Duration
    How much time is required to complete the activity?
    Highly dependent on the capabilities of the resources
  Cost
    (labor rate X duration) plus materials
    Systems, tools, etc.

## Slide 9: Estimating Guidelines
Get estimates from those responsible
Get multiple opinions / perspectives
  Delphi
Estimate based on “normal” conditions
  8-hour days, 80% availability, etc.
Use consistent units
Estimate independent tasks independently
Analyze the possible impact of risks

## Slide 10: Estimating Durations
Past experience is the best predictor
  Expert opinion
  Analogous estimating
    Look to previous, similar projects
  Parametric estimating
    Statistical basis based on significant parameters such as square footage, number of requirements, etc.
  Three-point estimates
    Expected = {[Opt. + (4 X Most Likely) + Pess.] / 6}
    Standard Deviation = (Pess. – Opt.) / 6
    Variance = (SD)2
Contingency reserves are OK, but don’t pad

## Slide 11: Refining and Finalizing Estimates
Account for “passing the baton”
Adjust for known “abnormalities”
Build in rework loops if necessary
Account for change (insurance contract?)
Schedule in refinement milestones
Establish contingency funds and time buffers where necessary for survival
  Use with extreme caution!
Track and store actuals for future analysis

## Slide 12: Getting into the Flow
Purpose of the Precedence Diagram
  Establish the relationships and dependencies among the project’s activities
  Optimize sequencing and analyze risks
  Begin planning resource allocation and scheduling
Inputs
  Work packages from the WBS decomposition
    The lowest level of decomposition
  Knowledge of activity relationships
Outputs
  Precedence diagram
  “Best Case” schedule
  Resource requirements

## Slide 13: Sequencing Activities
Define activities from the WBS work packages
  Activities consume time, money and effort to produce deliverables
Identify inter-activity dependencies
Graphically represent the sequence
Identify possible areas of improvement
  Parallel activity execution
  Minimize idle time
  Smooth resource utilization
Identify possible areas of risk
  Fan-in (merge) and fan-out (burst)
  Not enough room for error (slack)
  Inadequate resource pool
Refine the WBS as necessary

## Slide 14: Benefits
Validate estimates
Analyze interdependencies
Effective in developing the plan and helps set the stage for controlling the project
Communication vehicle
Risk management
Resource planning
Identify compression and other optimization opportunities
Helps to determine the viability of the project given available time, money, and resources

## Slide 15: Constraints
Constraints usually come from the following dependencies:
  Mandatory (hard logic)
    Work flow - one activity requires output from another
  Discretionary (preferred, soft logic)
    Best-practices dictate task ordering
  External
    Imposed from above (e.g., drop-dead dates)
    Availability of shared resources / unique skill set requirements
    Government regulations
    Supplier constraints

## Slide 16: Diagramming Basics
Arrows and Nodes
  Precedence diagramming method (PDM) depicts activity dependency relationships (preferred)
    Also known as activity-on-node (AON)
  Activity-on-arrow depicts state transitions
All WBS work packages must be represented
All activities must be exist on a path between the start and end nodes
Project networks
  Are acyclic
  Flow from left (project start) to right (project end)
  Have no conditional logic

## Slide 17: Types of Relationships
Finish-to-start (FS)
  Activity completion gives successor the green light
  By far the most common representation
Start-to-start (SS)
  Activity B cannot begin until activity A has started
  You must begin plowing before you can start sowing
Finish-to-finish (FF)
  B cannot finish until A has finished
  You must complete building before you can finish testing
Start-to-finish (SF)
  B cannot finish until A has started
  Don’t order the inventory until you’ve started preparing the warehouse
Most relationships can be converted to FS
  For example, subdividing tasks to achieve greater parallelism (known as laddering)

## Slide 18: Leads and Lags
Lead time
  Time removed from the schedule to bring an activity closer to the beginning of the project
  Example
    Painting is planned to begin once priming is complete
    The PM puts 1 day of lead in to begin the painting activity 1 day before the priming activity is finished
Lag time
  Slack built into the schedule to intentionally delay the start of downstream activities
  Example
    Putting in the carpeting can begin once the painting is done
    The PM puts in 1 day of lag to make sure the paint is dry

## Slide 19: Computing Duration
Forward Pass – Earliest Times (optimistic)
  Starts at 0 and computes ES and EF
  ESact + Durationact = EFact
  An activity’s ES is its predecessor’s EF
Backward Pass – Latest Times (risk averse)
  Starts at EF and computes LS and LF
  LFact - Durationact = LSact
  An activity’s LF is its successor’s LS
Slack is the cushion between early and late
  SL = LS – ES as well as LF – EF
  0 slack indicates a critical path activity

## Slide 20: Critical Path Analysis
Critical Path Characteristics
  Start to finish connection of activities with no float
  The path of longest duration
  Determines the project duration
  Any delay in a CP task slips the project end date
Critical Path Planning
  Manage CP tasks aggressively
  Watch for migration of the CP
Critical Chain Project Management
  Focuses on the CP as a significant project constraint

## Slide 21: Identifying Milestones
Choose points of significant accomplishment
  Successfully achieving a milestone should be reason to celebrate for the entire team
  Milestones should be focal points for the team
Choose points of transition
  Analogous to reaching a plateau when climbing a mountain
  A place to catch your breathe, reflect on what’s been accomplished, and re-evaluate the plan before moving on
Milestones must be clearly defined and attainable
Not too many, not too few

## Slide 22: Making It Real
Apply the network diagram to a calendar
  Real-time means account for holidays, weekends, meetings, downtime, etc.
Assign resources to the activities
  Match by skill set first,
  then look at availability
  Account for vacations, possible sick time, etc.
This is usually done with a GANTT Chart

## Slide 23: WBS to Schedule
Evolution of analysis
  All activities from the WBS analysis must be accounted for
  All dependency relationships from the Precedence Diagram must be respected
  Schedules are typically depicted in Gantt chart form
Resource Allocation
  Each activity must have a logical resource allocated to it (in terms of skills and experience)
  Resources must not be over-allocated