## Slide 1: Project Management for ITM ITM 471/571
Dennis Hood
School of Applied Technology
Fall ‘14
Notes: This template can be used as a starter file for presenting training materials in a group setting.
Sections
Right-click on a slide to add sections. Sections can help to organize your slides or facilitate collaboration between multiple authors.
Notes
Use the Notes section for delivery notes or to provide additional details for the audience. View these notes in Presentation View during your presentation.
Keep in mind the font size (important for accessibility, visibility, videotaping, and online production)
Coordinated colors
Pay particular attention to the graphs, charts, and text boxes.
Consider that attendees will print in black and white or grayscale. Run a test print to make sure your colors work when printed in pure black and white and grayscale.
Graphics, tables, and graphs
Keep it simple: If possible, use consistent, non-distracting styles and colors.
Label all graphs and tables.

## Slide 2
Week 1
Introduction and Motivation
Notes: This is another option for an Overview slides using transitions.

## Slide 3
Instructor
Notes: This is another option for an Overview slides using transitions.

## Slide 4: Dennis Hood
Background
  Teaching
  Industry
  Education
Contact
  dhood@iit.edu
  Office Hours
    TR 12:45pm – 1:45pm
    Or by appointment

## Slide 5
Objectives

## Slide 6: Course Objectives
Learn fundamental project management concepts
Explore techniques and methods designed to improve the likelihood of successfully delivering projects
Analyze case studies and simulations to experience project management

## Slide 7
Textbook

## Slide 8: Textbook
Effective Project Management: Traditional, Agile, Extreme, 7th Edition
  Wiley, 2014
  ISBN# 978-1-118-72916-8
We will also reference
  Guide to the Project Management Body of Knowledge (PMBOK), Project Management Institute (PMI)
  This is NOT a required text

## Slide 9
Grading

## Slide 10: Grading
Homework Assignments
Simulation Project
Individual Research Paper
Exam
Participation

## Slide 11
Motivation

## Slide 12: Be Prepared
Risk-based decision making
  How likely is it to happen?
  How much will it cost us?

## Slide 13: Motivation for Project Management
Projects fail at a ridiculous rate
  Significant direct expense is wasted
  Opportunity is lost
  Time and frustration may be “costliest”
Management can save the day
  Planning and monitoring help to minimize the impact of risks
  Change will happen and must be anticipated and embraced
  Management must be lean and effective

## Slide 14: Project Management Described
Added value
  Planning and monitoring help to minimize the impact of risks
  PM anticipates and manages inevitable change
  PM formalizes the process, a critical component for improving it over time
  The result is an increased likelihood that the current project will be successful and future projects even more so
Cost
  Management is overhead and therefore must strive to be lean and effective

## Slide 15: Project Management for IT Managers
Involves many diverse departments
Information Technology is a relatively immature discipline
The domains and technologies are extremely dynamic
They are also fairly expensive and somewhat resistant to change
Software development contains little standardization and almost no regulation
When a project is successful, the “how” is rarely documented for public consumption

## Slide 16: What is a Project?
General definition
  A project is a sequence of unique, complex, and connected activities having one goal or purpose and that must be completed by a specific time, within budget, and according to specification
Business focus
  A project is a sequence of finite dependent activities whose successful completion results in the delivery of the expected business value that validated doing the project (the business case)

## Slide 17: Project Definition Implications
A project is the application of resources (people, tools, etc.) to produce a product or deliver a service
Each project is temporary and unique
  It has a definite beginning and ending
  It has aspects that have never been done before
A project begins when the involved parties (stakeholders) agree to the objectives
A project ends when the objective (or an agreed upon modified objective) is met or is determined unattainable

## Slide 18: Examples
We manage projects in our daily lives
  “What should I have for breakfast?”
  “What do I want out of life?”
Ex: Attending class
  Objective: Arrive prepared, in the right place, and on time
Ex: Trip to a distant land
  Objective: See the sights and experience the culture (safety? budget?)
Ex: Build a building
  Objective: Meet the stated requirements including cost, schedule, and regulatory constraints

## Slide 19: Programs and Portfolios
Program
  A collection of logically related projects that share a common goal or purpose
  Managed in a coordinated way to obtain benefits and control not available if managed individually
  May include elements of related work outside of the scope of the discrete projects in the program
Portfolio
  A collection of projects or programs and other work that address strategic business objectives
  Grouped to facilitate effective management
  Not necessarily interdependent or directly related

## Slide 20: Inter-related Project Parameters
What we can accomplish (scope) and how good it is (quality) are factors of:
  How much we invest (cost)
  How long we take (time)
  And how hard we work (effort)
A change to any of these 5 factors forces a change to at least 1 of the other 4

## Slide 21: Death, Taxes and Change
Change is inevitable, don’t fight it
Technology will continue to change at a frightening speed
  Stay away from the bleeding edge
Next comes domain
  At a high-level of abstraction, the domain is fairly stable
Process will change the least
  That is where you should focus your efforts

## Slide 22: 21st-Century Challenges
Life-Cycle Compression
Globalization
Information Overload
Downsizing, outsourcing, off-shoring, etc.
Customer focus
More smaller projects

## Slide 23: Growth is Good, Creep is Bad
Scope creep
  Unmanaged and unaccounted for expansion of scope, typically driven by the customer
Feature creep
  Similar to scope creep, but typically driven by the project team (e.g., gold plating)
Hope creep
  Wishful thinking
Effort creep
  Working harder, not smarter

## Slide 24: Project Classifications
Each project is unique and therefore may require a unique management approach
However unique approaches are problematic
Better would be to develop a finite set of tailored approaches, each appropriate for a class of projects

## Slide 25: Classification by Characteristic
Projects can be classified by:
  The degree of risk
  The amount of business value
  Estimated duration
  Complexity
  Technologies to be applied
  Number of organizational units involved
  Estimated cost

## Slide 26: Classification by Project Type
Examples of project types:
  Application development
  System installation
  Recruiting and hiring
  Infrastructure implementation
  Vendor selection
  Policy development/establishment
  Research

## Slide 27
Week 2
The Project Management Process

## Slide 28: Lesson Overview
The PM Process
Reading: Ch. 2-3
Objectives
  Establish a process for managing projects
  Examine the life cycle of projects
  Analysis the role of stakeholders and other organizational elements in projects
  Discuss the PMBOK’s PM Processes and Knowledge Areas

## Slide 29
Definitions

## Slide 30: What Exactly Is Project Management?
What business situation is being addressed by this project?
What do we need to accomplish?
What will we commit to?
How will we do it?
How will we know that we did it?
When it’s over, how will we assess our performance?

## Slide 31: Definition of a Project
Ex.: Your car won’t start. You ask the mechanic to find out what’s wrong and fix it.
  Is this a project? Is it more than one project?
Ex: Your group is responsible for maintaining the XYZ system
  Is this a project?

## Slide 32: PM and Project Requirements
PM is an organized common-sense approach that utilizes appropriate client involvement in order to deliver client requirements that meet expected incremental business value
A requirement is a desired end-state whose successful integration into the solution delivers specific, measurable, and incremental business value to the organization

## Slide 33: Objectives and Constraints
Objectives are desired results and form the basis of project planning
  The project plan is designed to achieve the project’s objectives
  The project is done when the objectives have been met (generally speaking)
Constraints
  Restrictions on the structure of the project primarily associated with the parameters of the scope triangle

## Slide 34: Stakeholders
A stakeholder is anyone impacted by the project and/or its outcome
  Customer
  Sponsor
  Management
  Project team
  Partners, etc.
Proactive communication is critical to the stakeholders’ satisfaction

## Slide 35: Organizational Structure
Functional
  Organized by areas of specialization
  “Silos”
Projectized
  Organized by project teams
Matrix
  A combination of both
  Everyone has both a functional manager and a project manager

## Slide 36
Process

## Slide 37: PM Life Cycle Models
Linear
  Clearly defined and stable
Incremental
  Deliver business value early and often
Iterative
  Incomplete requirements
  Approach must facilitate discovery
Adaptive
  Big-picture goal understood, but not solution
Extreme
  Even the goal is not yet understood

## Slide 38: Project Management Processes
Process groups
  Initiating or Scoping
  Planning
  Executing or Launching
  Monitoring and Controlling
  Closing
The PM process can be instantiated several times during a project life cycle

## Slide 39: Knowledge Areas
Integration management
Scope management
Time management
Cost management
Quality management
Human resources management
Communications management
Risk management
Procurement management
Stakeholder management

## Slide 40
Week 3
Strategy, Scope and Initiation

## Slide 41: Lesson Overview
Strategy, Scope and Project Initiation
Reading: Chapter 4
Objectives
  Discuss the impact of business strategy on project management
  Explore methods for selecting the “right” projects given business objectives and resource availability
  Examine the process of pulling together the management elements crucial for project success
  Analyze organizational structure alternatives
  Examine the Initiation process group and the Integration Management knowledge area

## Slide 42
Strategy

## Slide 43: Organizational Mission
Strategic Management
  “You Are Here”; Destination and Plan
  How the organization plans to compete with available resources in current and anticipated environments
Steps for accomplishing the mission
  Define (or redefine) organizational mission
  Set long-range goals and objectives
  Analyze and formulate strategies
  Implement strategies through projects
  Go back to step 1 and repeat

## Slide 44: SMART Objectives
Specific
  Be unambiguous
Measurable
  Establish objective metrics
Assignable
  Identify accountability
Realistic
  Be sure it’s feasible
Time-bound
  Identify the finish line

## Slide 45: Strategic Projects
Projects are how strategies are realized
Implementation Issues
  Multiple dimensions of shared resources
  Prioritization
  Formal and informal coordination
  Authority and accountability
  Communication
  System support

## Slide 46: Governance
Project Classification
  “Must Do” vs. Operational vs. Strategic
Selection Criteria
  Alignment with strategic objectives
  Return on investment (over time)
  Resource availability
  Risk
Formal Proposal Process

## Slide 47: Project Proposals
Proposals capture relevant information
  Brief description (incl. category and timing)
  Risks
  Selection criteria ratings
Initial assessment screening
  Criteria weighting gives objective score
Formal Approval Process
  Signing authority based on total cost
Approved projects are prioritized

## Slide 48
Project Scope

## Slide 49: The Need for Project Definition
By “definition” we mean establishing the purpose and parameters of the project
  What will this project achieve?
  When will it complete?
  How many people?, having which skills?
  How much will it cost?
Consensus among stakeholders is critical to success
Definition must precede planning

## Slide 50: Scope of Work to be Performed
Scope defines the objectives and the work to be produced
  Begins as a client request and is negotiated into a contract of deliverables
  Must also define what won’t be done
  Establishes key milestones and environmental requirements
  Also agree to conditions of satisfaction
  Project scope vs. product scope

## Slide 51: Requirements
A requirement is something the product should do or a quality that it must have
The project’s scope is largely comprised of the product’s requirements
Requirements are gathered by analyzing customer needs, market trends, competitor’s products, etc.

## Slide 52: Testing Requirements
Completeness
  Have all requirements been captured?
Clarity
  Are they clearly stated?
Validity
  Do they accurately reflect customer needs?
Measurability
  Can each be measured?
Testability
  Can the implementation of each be tested for correctness?

## Slide 53: Testing Requirements (cont.)
Maintainability
  Will the implementation be maintainable?
Reliability
  Will the system be reliable/available?
Look and feel
  Will the system be adequately usable?
Feasibility
  Can the requirements be implemented?
Precedent
  Have we previously implemented something similar?

## Slide 54: Testing Requirements (cont.)
Scale
  Are the requirements large and/or complex?
Stability
  Are the requirements likely to change?
Performance
  Can performance requirements be met?
Safety
  Are safety issues adequately addressed?
Specifications
  Is documentation adequate?

## Slide 55
Organizational Structure

## Slide 56: The Need for Structure
Administration
  HR, budget, career development, etc.
Communication
  Command and control
Authority and Responsibility
  Accountability is essential
Functional Cohesion
  Skill and competency development
  Economies of scale

## Slide 57: Project Team Differences
Projects are temporary
  Project teams are only needed for a relatively short period of time
  They are expected to gel quickly and display a burst of productivity
Projects are cross-functional
  Membership is based primarily on value to the project (not historical ties, etc.)
  Understanding of roles is critical
Projects have a small set of well-defined objectives

## Slide 58: Option 1 – Functional
Surface Project from Functional Org
  Organize by function, Manage by project
Pros:
  Structural integrity
  Supports career paths
Cons:
  Focus is not on projects
  Project manager has limited authority
  Communication is strained

## Slide 59: Option 2 – Projectized
Organize the staff as project teams
  PMs have dedicated staff (senior managers)
  Some functional presence for operations
Pros:
  PM has direct authority
  Team is diverse, focused and unified
Cons:
  Difficult to optimize utilization (bench?)
  Consistent skill development is impeded

## Slide 60: Option 3 – Matrix Organization
Hybrid of 1 and 2
  PM’s “horizontal” authority overlays “vertical” functional hierarchy
  Weak vs. Balanced vs. Strong
Pros:
  More project-focused than hierarchy
  More efficient than project organization
Cons:
  Everyone has two bosses

## Slide 61
Project Initiation

## Slide 62: Project Initiation
Develop Project Charter (Integration Management)
  Purpose
  Business value
  High-level requirements
Identify Stakeholders (Communications Management)
  Highest level of roles and responsibilities
  Establish communication channels

## Slide 63
Integration Management

## Slide 64: Integration Management
Defines the overlap and interfacing among the activities of managing a project
  The PM’s reason for being
Most PM activities involve more than one knowledge area
  Cost estimates are dependent on time
  Risk management involves understanding the capabilities of the project resources, etc.
The IM knowledge area ensures that all PM processes are addressed
  Even if it is determined that a given process is not needed on a given project (tailoring)

## Slide 65: Integration Management Processes
Develop Project Charter
Develop Project Management Plan
Direct and Manage Project Execution
Monitor and Control Project Work
Perform Integration Change Control
Close Project or Phase

## Slide 66: Develop Project Charter
Formally authorizes the project and gives the authority to the project manager to allocate resources
  Statement of work
  Business case
  Measurable project objectives
  First-cut risk analysis
Approved by the project sponsor

## Slide 67: Develop Project Management Plan
Defines how the project will be executed, monitored and controlled, and closed
Encompasses plans for all of the other knowledge areas and plans for
  Change and configuration management
  Scope management
  Process improvement
Represents the result of tailoring the general project management process
Must be formally approved by stakeholders

## Slide 68: Direct and Manage Execution
Captures the integration piece of executing the project
  Basically making sure the project goes smoothly, especially at points of interaction
  Ensuring common understanding of project elements (e.g., responsibilities, etc.)
  Being of service (e.g., offer assistance, etc.)

## Slide 69: Monitor and Control Project Work
Tracking, reviewing, and regulating progress
Monitoring
  Collecting, assessing, analyzing, etc.
  Communicating status
Controlling
  Determining correcting or preventive actions
  Replanning if necessary

## Slide 70: Perform Integration Change Control
Change is a significant threat, but also a fact of life
Requests must be evaluated
  Impact/risk
  Time and effort required
  Cost
The implementation of formally approved changes must be managed
  Change Control Board (CCB)

## Slide 71: Close Project or Phase
The project doesn’t end with the completion of the technical work
  Formal acceptance of completion
  Final documentation
  Lessons learned analysis
  Capture of metrics and analysis
  Deliver final product and transfer responsibility
  Release project resources

## Slide 72
Week 4
Planning and WBS

## Slide 73: Lesson Overview
Planning Documents and Work Breakdown Structures
Reading: Chapter 5
Objectives
  Examine the planning process and associated documentation
  Analyze the process of defining scope
  Examine the Work Breakdown Structure (WBS) as a tool for establishing scope
  Analyze requirements verification and control

## Slide 74: The Planning Process Group
Develop Project Management Plan
Scope Management Planning
  Collect Requirements
  Define Scope
  Create WBS
Schedule and Budget Planning
Plan Quality and Develop HR Plan
Plan Communications
Risk Management Planning
Plan Procurements

## Slide 75: The Scope Management Processes
During Planning
  Collect Requirements
  Define Scope
  Create Work Breakdown Structure (WBS)
During Monitoring and Controlling
  Verify Scope
  Control Scope

## Slide 76: The Scope Statement
Describes the project’s deliverables and the work required to create them
Consists of:
  Product scope description
  Product acceptance criteria
  Project deliverables
  Project exclusions
  Project constraints
  Project assumptions

## Slide 77: Inter-related Project Parameters
What we can accomplish (scope) and how well we do it (quality) are factors of:
  How much we invest (cost)
  How long we take (calendar time)
  And how hard we work (resource effort)
A change to any of these 5 factors forces a change to at least 1 of the other 4

## Slide 78: Managing Project Priorities
Priorities determine which factors are:
  Constrained / Fixed – cannot be altered
  Enhance – should be optimized
  Accept / Tolerate – can be slackened
Factors must be negotiated to meet the objectives of the project while still maintaining the equilibrium of the scope triangle

## Slide 79: Work Decomposition
Breaking the goal into manageable pieces
Decomposition techniques
  Top-down vs. bottom-up
  Activities vs. deliverables
Stopping Rules
  Progress and completion can be measured
  Start and end events are clearly defined
  Each activity has a deliverable
  Effort can be estimated with confidence
  Required skills are well understood

## Slide 80: Work Breakdown Structures
A representation of the hierarchy of decomposed activities
  The top level represents the project’s goal
  The leaves represent the assignable work
  Intermediary levels represent “roll-ups” of related activities (phases, components, etc.)
Roll-ups
  Provide cost and effort summaries for logically-related activities

## Slide 82: Uses for the WBS
Helps analyze the project’s activities and deliverables
Helps frame the system architecture
Helps organize the project team
Helps analyze costs and establish budget
Provides a baseline for reporting status
Helps communicate work assignments and inter-dependencies

## Slide 83: Looking Ahead: Controlling Scope
Scope change may be the most significant threat to project success
  The initial effort to establish a clear understanding of scope is invaluable
  Disciplined change management must be employed to maintain control of the project
Progress will be measured in terms of activity completion
  Independent verification of completion
  Milestones

## Slide 84
Week 5
Risk Management

## Slide 85: Lesson Overview
Risk Management
Reading: Ch. 6
Objectives
  Explore the sources of risk and approaches for managing it
  Define risk in terms of likelihood and impact
  Analyze mitigation and contingency planning as part of project management

## Slide 86: Homework Assignment 1
You are the PM of a project which must complete on time to avoid a $500k fine
You have identified the following threats to on-time completion and estimated the likelihood of each:
  Not enough time (30%)
  Insufficient funding (20%)
  Insufficient effort (25%)

## Slide 87: Homework Assignment 1 (cont.)
Document your risk management plan
  Provide the exposure for each risk
  Provide a response plan for each risk
    Mitigation / transfer action(s)
    Estimated response cost and revised exposure
    Statement of cost vs. benefit
  Describe a plan to monitor each risk
    Metrics collection
    Contingency plan
Submit to Blackboard by 10/4/14

## Slide 88
The Risk Management Process

## Slide 89: Risk Management
Plan Risk Management
Identify Risks
Perform Qualitative Risk Analysis
Perform Quantitative Risk Analysis
Plan Risk Response
Monitor and Control Risks

## Slide 90: The Nature of Risks
Risk and opportunity go hand-in-hand
  Strategically taking risks and succeeding puts you ahead of the competition
  Risk-taking is energizing and unifying
Risk-taking expands knowledge
  Discovery comes from plunging into the unknown
Cost-Benefit is based on utility and exposure
  (Perceived) Benefit = Intrinsic Value + Actual Gain – Cost
  (Perceived) Loss = Intrinsic Impact + Actual Loss + Cost
  Expected Utility = Psuccess•Benefit - (1-Psuccess)•Loss
  Risk Exposure = Likelihood • Impact

## Slide 91: Planning
Inputs
  Scope and quality requirements
  Constraints
    Time, cost, resources, etc.
  Past history
Planning meetings and analysis
Risk management plan
  Framework for dealing with threats
  Responsibilities, general sense of impact, etc.

## Slide 92: Identify Risks: Tools and Techniques
Reflect on past projects to determine causes of past failures and near failures
Ask those being asked to commit
  Commitment leads to anxiety
  Anxiety reflects risk
Talk to the experts
SWOT analysis
  Strengths and weaknesses
  Opportunities and threats

## Slide 93: Identify Risks: Sources of Risk
Activity scheduling
  Activity dependencies and critical paths
  Time pressure
Organization and resource management
  Structure - Command, control and communication
  Human issues – team play, skills, experience, etc.
Funding
Scope creep and related changes
Ambiguous constraints, especially quality
Lack of process
New technology

## Slide 94: Risk Analysis
Qualitative
  Relatively quick initial assessment
  Fuzzy assessments of likelihood and impact at first (e.g., low, medium, high)
Quantitative
  Get to financial measure of exposure
  Likelihood is a probability
  Impact is a financial assessment
Prioritize by exposure ratings
Set aside “acceptable” risks

## Slide 95: Plan Risk Responses
Avoid
  Consider a different, risk-free approach
Transfer
  Transfer ownership to a 3rd-party
Mitigate
  Reducing the likelihood and/or impact
  May result in either transfer or avoidance
Accept
  Create a monitoring process
  Establish corrective actions

## Slide 96: Plans for Common Risks
Activity scheduling
  Insert buffers such as reviews
  Attend to the critical path
Organization and resource management
  Close communication gaps and look for cross-impacts
  Skills, experience and a good night’s sleep all matter
  Engage and involve the team
Funding
  Proactively manage the flow of cash
Scope creep
  Thoroughly analyze requirements then lock them down
  Make the users part of the process
  Establish and enforce change management procedures
Develop formal processes

## Slide 97: Dealing with Technology Risks
Technology changes frequently
  Keep projects short
  Anticipate upcoming advancements
Change leads to growth
  Establish a culture of R&D
  Reward prudent risk taking
Manage new technology insertion
  Provide adequate training
  Test drive before you commit
  Import expertise
  Participate in lessons-learned forums

## Slide 98: Cost-Benefit Analysis
Compare the cost of mitigation with the benefit (the reduced exposure)
  Exposure is a financial value
  Mitigation always costs something
  Benefit = ∆Exposure
Analyze completely
  Exposure changes with time
  Account for transferred risks

## Slide 99: Monitoring and Controlling Risks
Monitor the prioritized list of risks
Establish metrics and the associated measurement process for each risk
Determine triggers that will initiate action
Document the contingency plan for each
Recognize that monitoring is intrusive
Reassess risks frequently

## Slide 100
Week 6
Estimation and Control

## Slide 101: Lesson Overview
Estimation
Sequencing Activities (Precedence Diagrams)
Reading: Ch. 7
Objectives
  Develop methods for sequencing project activities
  Discuss techniques for optimizing networks
  Explore critical path management and other advanced sequencing topics
  Evolve project planning from WBS analysis to calendar scheduling

## Slide 102: Where is the Storm Going to Hit? End  date t, $  budegt
Pressure to provide an early answer can lead to errors and certainly lowers certainty
Change is inevitable (shorten to avoid this )
Variability due to risk is difficult to factor in
Political pressure to provide the right answer breeds cynicism
Fear of punishment breeds padding

## Slide 103: The Benefits of Good Estimating
Estimate Defined
  A credible approximation of the effort, time and cost required to successfully complete the project determined through careful analysis
Risk Reduction
  Enables more accurate resource planning
  Reduces the likelihood of running short or running out of critical resources
  Sets realistic stakeholder expectations
Motivates Early Analysis
Facilitates Communication
Improves Plan Credibility

## Slide 104: Estimation Challenges
Uniqueness
  History is the best predictor of future results
  Discovery will provide answers that lead to more accurate estimates, but we need an estimate now!
Complexity
  Many variables to consider
  May need to view multiple perspectives
Is the project team doing the estimating?

## Slide 105: Is Estimating Part of the Project?
Estimation takes time and resources
More such investment leads to more accurate estimates
Is this effort part of the project?
  Generally, initial estimates (macro) associated with project selection are not (Project Office and experienced personnel)
  More detailed estimates (micro) necessary to build the plan are (PM and key team members)
  This is largely semantics and accounting

## Slide 106: Estimating Activity Attributes
Finalize your definition of each activity
  Resources
    Skills required, desired level of experience, etc.
    Match with available (or attainable) resources
    Systems, tools, etc.
    Compile a resource calendar
  Duration
    How much time is required to complete the activity?
    Highly dependent on the capabilities of the resources
  Cost
    (labor rate X duration) plus materials
    Systems, tools, etc.

## Slide 107: Estimating Guidelines
Get estimates from those responsible
Get multiple opinions / perspectives
  Delphi
Estimate based on “normal” conditions
  8-hour days, 80% availability, etc.
Use consistent units
Estimate independent tasks independently
Analyze the possible impact of risks

## Slide 108: Estimating Durations
Past experience is the best predictor
  Expert opinion
  Analogous estimating
    Look to previous, similar projects
  Parametric estimating
    Statistical basis based on significant parameters such as square footage, number of requirements, etc.
  Three-point estimates
    Expected = {[Opt. + (4 X Most Likely) + Pess.] / 6}
    Standard Deviation = (Pess. – Opt.) / 6
    Variance = (SD)2
Contingency reserves are OK, but don’t pad

## Slide 109: Refining and Finalizing Estimates
Account for “passing the baton”
Adjust for known “abnormalities”
Build in rework loops if necessary
Account for change (insurance contract?)
Schedule in refinement milestones
Establish contingency funds and time buffers where necessary for survival
  Use with extreme caution!
Track and store actuals for future analysis

## Slide 110: Getting into the Flow
Purpose of the Precedence Diagram
  Establish the relationships and dependencies among the project’s activities
  Optimize sequencing and analyze risks
  Begin planning resource allocation and scheduling
Inputs
  Work packages from the WBS decomposition
    The lowest level of decomposition
  Knowledge of activity relationships
Outputs
  Precedence diagram
  “Best Case” schedule
  Resource requirements

## Slide 111: Sequencing Activities
Define activities from the WBS work packages
  Activities consume time, money and effort to produce deliverables
Identify inter-activity dependencies
Graphically represent the sequence
Identify possible areas of improvement
  Parallel activity execution
  Minimize idle time
  Smooth resource utilization
Identify possible areas of risk
  Fan-in (merge) and fan-out (burst)
  Not enough room for error (slack)
  Inadequate resource pool
Refine the WBS as necessary

## Slide 112: Benefits
Validate estimates
Analyze interdependencies
Effective in developing the plan and helps set the stage for controlling the project
Communication vehicle
Risk management
Resource planning
Identify compression and other optimization opportunities
Helps to determine the viability of the project given available time, money, and resources

## Slide 113: Constraints
Constraints usually come from the following dependencies:
  Mandatory (hard logic)
    Work flow - one activity requires output from another
  Discretionary (preferred, soft logic)
    Best-practices dictate task ordering
  External
    Imposed from above (e.g., drop-dead dates)
    Availability of shared resources / unique skill set requirements
    Government regulations
    Supplier constraints

## Slide 114: Diagramming Basics
Arrows and Nodes
  Precedence diagramming method (PDM) depicts activity dependency relationships (preferred)
    Also known as activity-on-node (AON)
  Activity-on-arrow depicts state transitions
All WBS work packages must be represented
All activities must be exist on a path between the start and end nodes
Project networks
  Are acyclic
  Flow from left (project start) to right (project end)
  Have no conditional logic

## Slide 115: Types of Relationships
Finish-to-start (FS)
  Activity completion gives successor the green light
  By far the most common representation
Start-to-start (SS)
  Activity B cannot begin until activity A has started
  You must begin plowing before you can start sowing
Finish-to-finish (FF)
  B cannot finish until A has finished
  You must complete building before you can finish testing
Start-to-finish (SF)
  B cannot finish until A has started
  Don’t order the inventory until you’ve started preparing the warehouse
Most relationships can be converted to FS
  For example, subdividing tasks to achieve greater parallelism (known as laddering)

## Slide 116: Leads and Lags
Lead time
  Time removed from the schedule to bring an activity closer to the beginning of the project
  Example
    Painting is planned to begin once priming is complete
    The PM puts 1 day of lead in to begin the painting activity 1 day before the priming activity is finished
Lag time
  Slack built into the schedule to intentionally delay the start of downstream activities
  Example
    Putting in the carpeting can begin once the painting is done
    The PM puts in 1 day of lag to make sure the paint is dry

## Slide 117: Computing Duration
Forward Pass – Earliest Times (optimistic)
  Starts at 0 and computes ES and EF
  ESact + Durationact = EFact
  An activity’s ES is its predecessor’s EF
Backward Pass – Latest Times (risk averse)
  Starts at EF and computes LS and LF
  LFact - Durationact = LSact
  An activity’s LF is its successor’s LS
Slack is the cushion between early and late
  SL = LS – ES as well as LF – EF
  0 slack indicates a critical path activity

## Slide 118: Critical Path Analysis
Critical Path Characteristics
  Start to finish connection of activities with no float
  The path of longest duration
  Determines the project duration
  Any delay in a CP task slips the project end date
Critical Path Planning
  Manage CP tasks aggressively
  Watch for migration of the CP
Critical Chain Project Management
  Focuses on the CP as a significant project constraint

## Slide 119: Identifying Milestones
Choose points of significant accomplishment
  Successfully achieving a milestone should be reason to celebrate for the entire team
  Milestones should be focal points for the team
Choose points of transition
  Analogous to reaching a plateau when climbing a mountain
  A place to catch your breathe, reflect on what’s been accomplished, and re-evaluate the plan before moving on
Milestones must be clearly defined and attainable
Not too many, not too few

## Slide 120: Making It Real
Apply the network diagram to a calendar
  Real-time means account for holidays, weekends, meetings, downtime, etc.
Assign resources to the activities
  Match by skill set first,
  then look at availability
  Account for vacations, possible sick time, etc.
This is usually done with a GANTT Chart

## Slide 121: WBS to Schedule
Evolution of analysis
  All activities from the WBS analysis must be accounted for
  All dependency relationships from the Precedence Diagram must be respected
  Schedules are typically depicted in Gantt chart form
Resource Allocation
  Each activity must have a logical resource allocated to it (in terms of skills and experience)
  Resources must not be over-allocated

## Slide 122: Homework Assignment 2
Project overview
  Develop a new software product
  Finish as soon as possible
    You must finish in 42 weeks or less to avoid a $1 million fine
    You will receive a $200k bonus for each week sooner than 42
  It would be nice if your budget was under $2.5 million
  You may need to make compromises to achieve “success”
Please see the activity details
  Durations are in weeks; Costs are in thousands of dollars
  Both the expected (“normal”) and the maximally compressed (“crash”) values are provided for each activity
  Activity dependencies are also provided with the listing of each activity’s predecessor(s)
  In addition to the given activity costs, your project will incur a $2k per week administrative overhead fee

## Slide 123: Homework 2 – Activity Details

## Slide 124: Homework 2 - Deliverable
Define “success” for this project
Draw a precedence diagram for the "normal" schedule
  show the critical path(s)
  expected project costs (indirect, direct and total)
  expected project duration
  justify any assumptions
Advise the team of their situation
  Use our compression algorithm to identify options
  Draw a project cost-duration graph showing all solutions
  Choose the “best” plan and use cost-benefit analysis to justify your selection
  SHOW ALL WORK and JUSTIFY ALL ASSUMPTIONS!
Due 10/18/14

## Slide 125
Week 7
Schedule Management

## Slide 126: Lesson Overview
Schedule Management
Reading: Ch. 9
Objectives
  Explore scheduling issues and approaches to effective schedule development
  Analyze scheduling and resource allocation techniques
  Revisit risk management with regard to scheduling decisions
  Define “Traditional Project Management”

## Slide 127: Identifying Milestones
Choose points of significant accomplishment
  Successfully achieving a milestone should be reason to celebrate for the entire team
  Milestones should be focal points for the team
Choose points of transition
  Analogous to reaching a plateau when climbing a mountain
  A place to catch your breathe, reflect on what’s been accomplished, and re-evaluate the plan before moving on
Milestones must be clearly defined and attainable
Not too many, not too few

## Slide 128: Making It Real
Apply the precedence diagram to a calendar
  Real-time means account for holidays, weekends, meetings, downtime, etc.
Assign resources to the tasks
  Match by skill set first,
  then look at availability
  Account for vacations, possible sick time, etc.
This is usually done with a GANTT Chart

## Slide 129: WBS to Network to Schedule
Evolution of analysis
  All activities from the WBS analysis must be accounted for
  All dependency relationships from the Network Diagram must be respected
  Schedules are typically depicted in Gantt chart form
Resource Allocation
  Each activity must have a logical resource allocated to it (in terms of skills and experience)
  Resources must not be over-allocated

## Slide 130: Know Your Critical Path
The critical path dictates the project’s duration
  All other paths contain float
Delays to critical activities delay the project
  Manage risk along the CP aggressively
    Dependable resources
    Milestones and quality reviews
    Strategic buffers
Compression is only possible along the CP
  Compressing a CP activity will compress the project by the same amount as long as enough float exists in the non-critical paths

## Slide 131: Critical Chain Method
Goldratt, The Goal and Critical Chain
  Theory of Constraints
  Respects both resource and technical constraints
Observations
  People pad estimates
  But people tend to use the padding
  Early completion is often not reported so the opportunity is lost
  Multitasking overhead is under estimated
  A few key resources truly drive the project and therefore bottlenecks are created around people
  People procrastinate

## Slide 132: Pressure to Compress
Reasonable sources of pressure
  Time is money
    Though not completely correlated: if the project completes sooner it will cost less
  Market windows and competition
  We all know you padded the schedule!
Unreasonable sources of pressure
  Management is trying to appease
  We have to fit the budget cycle
  We’re late!

## Slide 133: Getting it Done Sooner (or Cheaper)
Respect the scope triangle
  Reducing time usually increases cost
  Unless scope and/or quality is sacrificed
Focus on critical path activities
  You can only reduce total project duration by reducing critical path activity durations
  Remember – compression creates new CPs
Reassess risk
  Schedule compression is inherently risky
  Beware the Mythical Man Month (Brooks)

## Slide 134: Compression Options
Feasible
  Reduce scope
  Phased-delivery, throwaways and prototypes (extreme programming)
  Outsource
  Dedicated project teams
  Fast-track and crashing
Risky
  Add resources
  Schedule overtime
  Compromise quality
Wishful thinking

## Slide 135: Compression Cost-Benefit Analysis
Assuming compression is feasible (safe, respects scope triangle, etc.) we still need to assess its value
  Is the benefit of the compression worth the cost?
  Remember, crashing has its limits and is inherently risky
Project indirect costs
  Overhead that varies directly with time
  Administration, supervision, rent, etc.
  The shorter the project, the lower the indirect cost
Project direct costs
  Driven directly from activities
  Labor, equipment, subcontractors, etc.
  Can the activity be done faster? At less cost?

## Slide 136: Compression Analysis Graphs
Project Cost-Duration Graphs
  Graph the total project direct, indirect, and sum costs by time for each feasible project duration
  Identifies the optimum cost-duration point
Activity Graphs
  Examines the cost per unit time of an activity
  Activity costs assume “normal” time
  Activities can be “crashed” at a cost (scope triangle)
  Goal: crash CP activities with the smallest increase in cost per unit time

## Slide 137: Compression Algorithm
Calculate the cost to compress each activity by one unit of time (slope)
Identify the CP activities
  Compress the project by one unit of time by compressing the activity (or combination of activities) with the lowest cost (smallest slope)
    It may be necessary to compress more than one activity if there are multiple CPs
    Compress each activity by only one unit of time per iteration
Recalculate the CP
Iterate steps 2-4 until “done” compressing

## Slide 138: Resource Allocation
Resources extend from human to materials, equipment and working capital
Utilization
  Both over and under-utilization can cause problems
  Keep people engaged but leave breathing room
  Projects are more marathon than sprint
Smoothing
  Take advantage of available float
  Switch assignments if feasible
  Adjust dependencies if necessary

## Slide 139: Multiproject Scheduling
Benefits
  Improved global utilization
  Key resources provide skills and experiences to more than one project
  Increased employee engagement
Risks
  Multiple-boss problem at the project level
  Schedule changes in one project can create conflicts with another
  Project switching overhead can decrease effectiveness

## Slide 140: Managing Risk in Scheduling
Things requiring risk management
  Merges and bursts
  Critical path activities
  Heavily utilized resources
Variability is risk
  Risk accumulates with each activity
  Seems like we’re late more often than early

## Slide 141: Measuring and Reporting Status
Measure progress vs. plan
  Has the milestone been achieved?
  Has the deliverable been produced? To satisfaction?
  To what degree has the activity been completed? To satisfaction?
Document and communicate progress
  Status reports should report on activity completion
  Reporting should be sequenced to allow for effective review
  Deviations from plan must follow risk and change management plans

## Slide 142: Scheduling for Success
Allocate resources to match required skills and experience levels
Mitigate schedule risks with strategic buffers
Make the most of your milestones
  Measurable
  Attainable
  Useful
Build a schedule you can manage
  Measure and document progress
  Manage change effectively

## Slide 143: Traditional Project Management
Linear PM Life Cycle (PMLC) Model
  Dependent phases executed sequentially
  Best if
    Scope is well defined and not likely to change
    Activities are fairly routine (predictable)
    Established templates can be utilized
Incremental PMLC Model
  Dependent phases repeated in sequential order (still no feedback)
  Best if
    Interim deliverables (partial solutions) are desirable
    “Final” deliverable is not completely understood
    Some scope change is expected due to “on-the-fly” clarification
    Resources are scarce and must be allocated more dynamically

## Slide 144
Week 8
Cost Management and EVM

## Slide 145: Lesson Overview
Cost Management and Maintaining Control
Reading: Chapter 9
Objectives
  Discuss the activities required to manage project costs
  Examine methods for establishing and managing project budgets
  Discuss monitoring as a process for keeping projects on target
  Identify metrics that facilitate effective monitoring as well as methods for collecting and using them effectively
  Examine the earned value approach to monitoring projects

## Slide 146: Cost Management
Estimate costs
  Direct costs
    Labor effort over time
    Systems, tools, materials, etc.
  Indirect costs (administration, etc.)
Establish budget
  Expenditures over time
  Justification of costs
Control costs
  Establish baseline
  Measure actual and compare to plan

## Slide 147: The Cost Management Plan
Overrunning the budget is a significant project risk that must be managed aggressively
The Cost Management Plan is part of the overall Project Management Plan
  States how costs will be estimated and planned, and
  how actual expenses will be managed with respect to the plan
The following should be considered during planning:
  The required level of accuracy for cost estimates
  The units of measure for each cost driver (e.g., “per week”)
  Control Account codes to link costs to organizational units
  Control or variance thresholds for triggering contingencies
  The rules for measuring performance (e.g., EVA)
  Reporting formats and frequency – different stakeholders may have different needs/requirements
  The inclusion of indirect costs (e.g., administrative overhead)

## Slide 148: Estimating Costs
Let past experience help predict the future
  The same methods used to estimate time
Time is money – so look to duration estimates
  Estimate how much it will cost to successfully complete each activity
  The schedule usually drives the budget, but consider altering the schedule to get a better budget (e.g., materials may be cheaper if purchased sooner or later than originally scheduled)
Non-labor resources (e.g., systems, tools, etc.) cost money too
Don’t forget to pay yourself (PM activities)
Strategically allocate reserves, but don’t pad!

## Slide 149: Estimation Accuracy
Generally speaking, increasing the accuracy of an estimate will take more time and effort
  Rough Order of Magnitude (ROM) Estimate
    Usually made during project initiation
    Typically a range of +/- 50% from the actual cost
  Budget Estimate
    Usually made during project planning
    -10 to +25% from actual
  Definitive Estimate
    Refinements made during the project
Generally speaking, the more accurate an estimate is, the more valuable it will be

## Slide 150: Determining the Budget
The process of aggregating estimated costs to establish an authorized cost baseline
  How much money should the organization prepare to expend in total?
This includes contingency/reserve funds that should be set aside to recover from risks
  Contingency funds are associated with known risks
  Management reserves can be added to the budget to cover “unknown” risks such as unplanned scope changes
Cash flow analysis is necessary to ensure that required funds are available when needed

## Slide 151: Controlling Costs
Actual project performance must be monitored and controlled to ensure adherence to the plan and, if necessary, to trigger contingencies to recover from deviations
Controlling the project from a cost perspective
  Collect expenditure data
  Compare with planned cash flow (limited value)
  Incorporate “true” project progress (earned value)
  Trigger contingency if variance exceeds threshold
  Report budget status
Increases in the budget must be formally approved

## Slide 152: Monitoring Progress
Goals
  Keep the project on target (“You Are Here”)
    Implies the presence of a baseline
  Feed data to risk and change control
  Provide visibility for stakeholders
  Collect data for the knowledge base
Monitoring is inherently intrusive
  Take what is readily available
  Extract the rest carefully
  Keep the process objective and positive
Are people more productive when they are being watched?

## Slide 153: What to Measure
Progress
  How far along is the project?
  Are we hitting our milestones?
  How much is left?
Stability
  How frequently is the direction changing?
  Are we in control? Is control attainable?
Quality
  How “acceptable” are the work products?
  Do we need to “rework” anything?

## Slide 154: Earned Value Management
Combines time, cost, and work completed
  Used to determine project status
  How much value has been created to date?
  Implies the existence of a phased budget and the ability to collect actual cost and progress over time
Base metrics
  Planned Value (PV)
    estimated value of work planned to date
    PV at the target completion date equals the budget (BAC)
  Earned Value (EV)
    estimated value of work actually completed
  Actual Cost (AC)
    actual cost of the work actually completed

## Slide 155: EV Derived Metrics
Variance – difference from plan
  Cost Variance (CV) = EV - AC
  Schedule Variance (SV) = EV - PV
  Cost Performance Index (CPI) = EV / AC
  Schedule Performance Index (SPI) = EV / PV
Forecasting completion
  Estimate at Completion (EAC)
    As of now, how much do we expect the project to cost?
    At planned rate of spending vs. at actual rate of spending
  Estimate to Complete (ETC)
    Estimated remaining cost
  Variance at Completion (VAC)
  To-Complete Performance Index (TCPI)
    Rate to meet in order to stay within budget

## Slide 156: Using Earned Value Analysis
Variance analysis
  Compute the schedule and cost variances
  Positive is good, negative indicates lag relative to plan
Efficiency analysis
  Compute CPI and SPI
  <1 indicates inefficient relative to expectations

## Slide 157: Using Metrics to Improve the Process
Capability Maturity Model (CMM)
  Each level is characterized by increasing proficiency at monitoring
  Achieving a CMM level requires quantitative proof of capability
Feedback Loops
  Educate the team on what did and didn’t work
  Metrics make it objective
  Gets the team focused on areas in need of improvement and the size of the gap
Historical Data
  Along with experience, the project manager’s best friend

## Slide 158
Week 9
Stakeholder and Quality Management

## Slide 159: Lesson Overview
Stakeholder and Quality Management
Reading: Chapter 16
Objectives
  Examine the process of quality management and its relationship to project management
  Analyze methods for assuring acceptable levels of quality
  Discuss the role of stakeholder management in projects
  Analyze leadership and conflict management

## Slide 160
Stakeholder Management

## Slide 161: People: Your Most Valuable Asset
Success or failure will primarily be driven by the performance of your team
  Attitude, motivation, etc.
Their development on your project is critical to the success of the organization
  Maturity, professionalism, team attitude, etc.
People management is very dynamic
  Shared resources, outside influences, etc.

## Slide 162: Roles and Responsibilities
The team
  Work as a team to complete project activities
The sponsor
  Provides funding, resources, guidance, etc.
Functional managers
  “Own” the resources and provides technical direction
The project manager
  Leads, manages and controls

## Slide 163: PM Responsibilities
Determine required resources
Work with functional managers
Establish and maintain team cohesion
Manage the team
Communicate responsibilities
Manage stakeholder relationships
Provide tools and training
Evaluate performance

## Slide 164: The Human Resource Plan
Enterprise environmental factors
  Culture, policies, availability of assistance, etc.
RACI chart
  Responsible, accountable, consult, inform
Staffing management plan
Recognition and rewards systems

## Slide 165: Project Leader Contradictions
Be involved but not too involved
  Think holistically, attend to detail
  Communicate broadly and proactively
Innovate while maintaining stability
See the big picture while executing tasks
  Rely on intuition
  Understand the business and politics
Be decisive and flexible
  Maintain composure and be unwavering
  Act with (measured) urgency, justice and integrity
  Motivate (by example) and be optimistic
Champion individuals but stress teams
  Partner with others and value teams
  Unite and protect the team while respecting the organization

## Slide 166: The Power of Teams
Diversity of thought
  Comprehensive exploration of the solution space
  Complex problems have many possible solutions
  Teams are more likely to identify and analyze a richer set of possible solutions
Inertia
  The momentum of a team is more sustainable than that of individuals
Learning through sharing
  Training of individuals is expensive and often inefficient
  Shared experiences provide more efficient and longer lasting training

## Slide 167: Leading Teams
Communicating vision and purpose
Acting with integrity and justice
  Evaluating team and individual performance
  Recruiting and evolving
Maintaining high performance levels over long periods of time
  Motivation and inspiration
  Downtime and change
  Leading by example

## Slide 168: Group Decisions and Conflict
(Managed) conflict is good
Consensus on a team is better than individual opinions
  Establish a culture of respect for opinions
  Establish effective forums for idea sharing
  Encourage and manage productive conflict
Consensus is easier said than achieved
  Group think is like a big individual opinion
  What if there’s no clear winner?
  Unresolved conflict can fester

## Slide 169
Quality Management

## Slide 170: Quality Defined
Quality
  The degree to which the project fulfills requirements
  A degree of excellence
  A critical yet understated requirement
Quality Management
  Creating policies and procedures
  Enforcing them to ensure compliance with project requirements

## Slide 171: QA vs. QC
Quality Assurance
  Prevent defects
  Improve the level of quality through an efficient set of activities performed throughout the life cycle
Quality Control
  Eliminate defective products
  Improve the rate of acceptable product delivery through an efficient set of defect detection activities, primarily late in the life cycle

## Slide 172: Quality Goals
Prevent, discover and eliminate defects
Deliver customer satisfaction by representing the user in design and development
Enforce standards and process
Mind the gate
Improve processes
Review, audit, monitor, verify, validate and inspect

## Slide 173: The Value of Quality
Quality increases customer satisfaction
  Credibility lasts and attracts new business
Lack of quality leads to rework
  Unscheduled work means unplanned expense and slipping schedules
  Work under duress increases the likelihood of more mistakes
Uptime and performance are largely determined by quality
  Lack of quality drives the need to change

## Slide 174: The QA Environment
Contractual conditions
  Scope, time, budget, etc.
Customer-supplier relationship
  Change management, acceptance, etc.
Teamwork
  Variety of skills, parallel activities, etc.
Multiple project support
HCI / usability concerns
Turnover management
Maintenance
  Enhancement and release management, troubleshooting, etc.

## Slide 175: Defect Classification
Incorrect specification of requirements
Misunderstanding of client’s needs
Deviation from requirements
  Gold-plating, short-cutting, etc.
Design errors
Implementation errors
Violation of standards
Poor test coverage
User interface / usability errors
Documentation errors

## Slide 176: Planning for Quality
Checkpoints supporting milestones
Independent verification
Build-test-fix-retest
Make it measurable/testable
Inspire the delivery of high-quality deliverables
  Establish quality goals
  Obtain commitment
  Motivate performance
Collect the data/information required to improve over time

## Slide 177: Analysis Tools
Control Charts
  Maintain stability within upper and lower limits
Benchmarking
  Actual vs. past performances
Design of Experiments
  Identify factors influencing specific variables,
  so that they can be managed
Statistical Sampling
  When evaluating all or most is impractical
Flowcharting / process analysis
  Anticipation of troublesome steps

## Slide 178: Perform Quality Control
Feedback loops
  Measure the output of a process
  As compared to expected
  Understand the results (both good and bad)
  Use that knowledge to improve the process
Root-cause analysis
  Ask yourself what caused a problem to occur,
  then ask what caused that cause, and so on
Histograms and Pareto Charts
  Frequency of problems by problem category
  80% of the problems are due to 20% of the causes
  Invest in eliminating the most problematic causes

## Slide 179: Case Assignment #3
Scenario
  Last year your company committed to a very challenging project because your best engineers “guaranteed” they could handle the challenges and deliver the final product on time – you are the project manager
5-month status report
  The engineers report that all is going well
  Accounting reports that the project is on budget
10-month status report
  The customer is on the phone asking for the finished product
  Accounting reports the entire budget has been spent
  The engineers report they are not ready and will need 5 more months (accounting reports this will cost an extra $500k)
  They again guarantee success stating that the problems were due to using unfamiliar, complex technologies

## Slide 180: Case Assignment #3 (cont.)
Analyze the state of the project
  Draw an EVM graph
    Plot the PV, EV and AC lines
    Plot points for 0, 5, and 10 months
    Estimate EV and AC for 100% completion (show on the graph)
  Recommend and justify next steps
    Calculate SV, CV, SPI and CPI at 5 and 10 months
    Recommend changes to complete the project by month 13
Analyze the state of the company
  Who should be fired (and why)?
  Document a process improvement plan stating specific changes to make future projects more likely to succeed
Due 11/15/14 (Blackboard)

## Slide 181
Week 10
Closing Phases

## Slide 182: Lesson Overview
Auditing and Closing Projects
Reading: Chapter 8
Objectives
  Discuss activities associated with closing things – contracts, phases, projects, etc. – such as audits, lessons learned analysis, etc.
  Discuss the role of contracting and purchasing
  Examine different types on contracts and strategies for entering into them
  Analyze buy vs. build-type decision making

## Slide 183
Closing Phases

## Slide 184: Achieving Milestones
Closure
  Managing phase closure is critical to future success
  This applies to interim phases as well as the project as a whole
Analysis
  Capture metrics
  Assess state
Stakeholder management
  Record and report
  Obtain approval and move on
Keys to success
  Start with the end in mind
  Be disciplined (no cutting corners!)
  Celebrate success
  Learn

## Slide 185: Are We There Yet?
The project is done when:
  You deliver the deliverable and the customer accepts it
  The stakeholders agree to end it
  Never, it will go on forever!
  It fails (and everyone admits it)
  It’s cancelled (due to outside influences)
The ability to accurately assess the state of the project is key

## Slide 186: A Time of Reflection
Audit goals
  Identify the successes and failures
  Gain an understanding of why (root causes)
  Learn and record the knowledge
The process
  Start with objective actual vs. planned data, then supplement with testimonials
  Identify significant goods and bads
  Do the detective work to determine the true sources
  Record the lessons learned for future improvement

## Slide 187: Keys to an Effective Audit
It’s not about blame
  Chances are it was more process than person anyway
Focus on the big items
  Chances are solving them will probably correct the little ones anyway
Try to balance positives and negatives
  No project is all good or all bad
  You can learn as much from your successes
Get a good scribe

## Slide 188: Questions to Address
Did the team follow the plan?
Was the schedule appropriate? budget?
Did the PM lead effectively? manage?
Was the team cohesive and effective?
Did we have the right people? tools? training?, etc.
Was risk managed well? change?
Was communication proactive?
Were we able to do it right?

## Slide 189: Evaluating Performance
Start with teams, then look at individuals
Gather feedback from multiple sources
Be objective, fact-based, honest and just
Keep true to the accountabilities established during planning
Emphasize successes and areas in need of improvement
Reward those who made it happen

## Slide 190: Where Do We Go From Here?
Celebrate success, or at least the accomplishment of completion
Respect the team’s momentum and comfort with each other
Look for opportunities to advance individuals
Relax, reflect and refresh
Do it again - only this time do it better!

## Slide 191: Procurement Management Process
Obtaining the supplies, resources, services, etc. required by the project
  Buying from a seller
Issues
  Rules and regulations
  Negotiation and relationships
  Buy vs. build
  Useful life
Steps
  Plan - identify needs, evaluate sellers, etc.
  Conduct - negotiate and select sellers
  Administer – manage relationships, change, etc.
  Close

## Slide 192: Procurement Contracts
Contracts are binding and must therefore be respected
  It can be both shield and sword – either for or against you!
  Change management discipline is key
  The project manager should be involved in developing the contract

## Slide 193: Procurement Decisions
Determine need
Buy vs. build vs. borrow
  Risk is a cost
  Time has value
Seller selection
  The pros and cons of “preferred” vendors
  Capability, including relevant experience
  Motivation
Post-engagement responsibilities
  Ownership
  Maintenance

## Slide 194: Paperwork
Statements of work (SOWs)
Requests for proposal (RFPs)
  Also requests for bids or quotes
Purchase orders (POs)
Contracts
  Fixed price vs. Time and material vs. Cost reimbursable
  Delineation of responsibilities
  Acceptance
Nondisclosure agreements

## Slide 195: Administer Procurements
Disciplined change management
Quality assurance
Verifiable completion of scheduled work
Proactive communication
Risk monitoring supported by EVM

## Slide 196: Project Maturity Model
Organizational Project Maturity Model
  Developed by the PMI
  Modeled after SEI’s CMM
Levels of maturity
  Ad hoc – Lacks predictability
  Formal – PM standards are applied
  Institutionalization – Organization-wide
  Management – system support for portfolio management
  Optimization – Continuous improvement

## Slide 197
Week 11
Process Improvement and PM Models

## Slide 198: Lesson Overview
Process Improvement and PM Models
Reading: Chapter 12
Objectives
  Examine the topic of process improvement as it pertains to the project management process
  Discuss approaches for improving the PM process
  Analyze the role of metrics in improving the PM process
  Compare and contrast different PM models

## Slide 199
Process Improvement

## Slide 200: Improving a Process
Processes are inherently improvable
  The more you examine a process the more imperfections you’ll spot
  Just when you think you’ve squeezed out all of the inefficiencies, along comes a technology innovation!
Improvements should be strategic
  Make decisions based on benefits and costs
Change is hard so be gentle

## Slide 201: Motivation
Change is a constant threat
  IT managers rely on the unreliable – people and tools
  People use tools in the context of a process to (hopefully) create value
  Processes are often more manageable and stable
Knowledge is power
  Understanding the “as-is” allows us to move methodically (and strategically) toward the “to-be”
  Decreasing inefficiency and increasing productivity results in greater profit

## Slide 202: The Physics of Process Flow
Bottlenecks
  Where is the flow most restricted?
Friction
  Is the flow inhibited? (bureaucracy, etc.)
Inertia and momentum
  A process at rest tends to stay at rest
Conductivity and insulation
  Do motivators exist to encourage positive flow?
  Is the process isolated from “distractions” and “noise”?

## Slide 203: Variability of Process
Variety
  The spice of life
  Death to a production line
Managing variability requires knowledge of
  The desired output
  The degree of tolerance
Reducing variability (increasing predictability) takes effort ($)
Side benefits can be significant

## Slide 204: Goal-based Improvement
Focus on improvement
  A focal point is essential to achieving significant, sustainable improvement
Don’t try to get it all in one swing
  If the end of the tunnel is so far away that we can’t see the light, then we need interim goals
  Success is a journey – just keep heading in the right direction

## Slide 205: The Role of Feedback
Get connected
Timing is everything
Be SMART
Thresholds are necessary to prevent overreaction
Proactivity vs. reactivity
  Is it process improvement or quality control?

## Slide 206: Quality Focus Thru the Years
The assembly line
TQM
ISO 9000
Deming
Baldridge
CMM
Six Sigma

## Slide 207: Six Sigma: Methodology or Religion
Process change, Six Sigma style
  Management
  Improvement
  Redesign
Zen and the art of process improvement
  If you look closely enough, you will see variation
  If you focus on it, will it improve?

## Slide 208: Six Sigma Mechanics
No more than 3.4 defects per million opportunities (DPMO)
Implies that
  We know (exactly) what a defect is
  We know (exactly) what an opportunity is
  We have a measurement process that
    Accurately detects any defect
    Is unobtrusive enough so as not to significantly impede productivity

## Slide 209: Statistically Speaking
Six Sigma assumes a normal distribution (bell curve) of event outcomes
99.99966% of outcomes will be within six standard deviations of the mean
  In other words, only 3.4 of every million outcomes will be outside the six standard deviation range
It only works if
  You really have a normal distribution
  You target the mean and
  You bound your acceptable range of outcomes at -/+ six standard deviations

## Slide 210: Six Sigma Projects
Define requirements
  Suppliers, Inputs, Process, Outputs, Customers (SIPOC)
  Critical-to-Quality (CTQ)
Measure existing vs. desired
  Focus on the “important” outputs that can be improved
Analyze data to identify causes
Improve the process
Control the results and maintain

## Slide 211: The Capability Maturity Model
Developed to address software project failure rates
  US Defense Department (DoD) and the Software Engineering Institute (SEI)
  Lack of maturity of process in engineering software was believed to be the leading cause of an alarming failure rate
A framework for improvement
  Five distinct levels of process maturity
  Key process areas that must be satisfied

## Slide 212: CMM’s Levels
Initial (aka ad hoc, chaotic, disorderly)
Repeatable
  Disciplined enough to repeat successes
Defined
  Defined and documented process, tailored
Managed
  Quantitatively understood and controlled
Optimizing
  Continuously improving

## Slide 213
PM Life Cycle Models

## Slide 214: PM Life Cycle Models
Linear
Incremental
Iterative
Adaptive
Extreme

## Slide 215: The Linear Model
Waterfall approach
  Scope
  Plan
  Launch
  Monitor & Control
  Close
Phase relationships are finish-to-start
Very well understood goal and solution
  “We’ve done this many times before”
Intolerant of learning / change

## Slide 216: The Incremental Model
Piecemeal version of the waterfall approach
Phased deliverables provide earlier, lesser value in increments
Learn as you go – change as necessary

## Slide 217: The Iterative Model
Iteration is used to explore, discover and learn while moving toward an acceptable level of completion
Iterations produce increasingly complete prototypes to facilitate discovery of the complete solution
Scope can be “refined” between each iteration

## Slide 218: The Adaptive Model
The future is less certain
Knowledge gained in one iteration will be used to direct the next iteration
  Just-in-time planning
The goal is convergence toward an acceptable solution
  High-risk, high-reward?
Partial solutions may be released at the discretion of the client

## Slide 219: Extreme Project Management
Rapid and very visible progress toward a yet to be determined solution to a vague and evolving problem
Capability and desire in search of a solution which in turn will search for a problem
Change is a given since the next iteration is at best loosely defined until the current iteration is assessed
Success must be thought of in different terms – knowledge gained

## Slide 220: Extreme PM Evaluated
Strengths
  Extremely engaging (creative problem solving)
  Extremely flexible
  Rapid breezing over of many possible solutions
  Facilitates getting “out of the box”
Weaknesses
  Commitment to anything but exploration is futile
  Encourages play, not work
  Drives sales and marketing crazy
  Who’s paying for this?

## Slide 221
Week 12
Challenging Projects

## Slide 222: Lesson Overview
Distressed and Multi-team Projects
Reading: Chapters 13 and 14
Objectives
  Examine especially challenging project management situations
  Analyze the root causes of distress and discuss approaches for preventing such situations
  Discuss challenges associated with multi-team projects and approaches for managing them

## Slide 223
Challenging Projects

## Slide 224: Distressed Projects
The project seems headed for failure
  EVM variance metrics
    Trending toward failure over a significant duration
    Recent metrics indicate a high risk of failure
  A recent significant change threatens project success
    Key personnel quit or become unavailable
    Dramatic change in scope
    Project de-prioritized by management
    An “uh-oh”-moment (e.g., tool limitations)
    Money troubles
    A “fire” breaks out with in production

## Slide 225: Root Causes
Inadequate requirements capture
Lack of sponsorship
Lack of planning, risk analysis, etc.
Poor management of change
Lack of oversight (monitoring)
Over commitment / wishful thinking
Poor communication / lack of visibility
Inadequate training and/or technology evaluation

## Slide 226: Don’t Let This Happen to You
Learn from the past
  Or else, history will likely repeat itself
Take the time to manage risk
Line up sponsorship
Plan with detail (WBS, budget, etc.)
Manage the critical path
Manage change with discipline
Respect the dynamics of people and teams
EVM-based checkpoint control

## Slide 227: Reporting Status
Be concise
  140 characters or less?
Convey facts clearly (progress, issues, etc.)
  Metrics, simple graphs, etc.
Project optimism and control
  It’s all about the plan
Be realistic
  Inform, don’t sell
When necessary, raise the alarm loudly
  Manage expectations
  Obtain help

## Slide 228: Contingency Plans
Developed during risk planning
Be prepared to obtain more effort, more time, more money, etc.
Monitor risks closely, focus on triggers
Change course if necessary, but do so with care
Learn and improve next time

## Slide 229: Multi-team Projects
Collaboration and involvement of 2 or more teams
  All project teams have multiple sub-teams
Crossing “political” boundaries is risky
  The 2-boss problem of the matrix
  Internal cultural differences
  Managing contractors is especially hard
Command, control, communication
PMs must delegate to (trusted) sub-team leads

## Slide 230: Multi-team Keys for Success
Communication
  Proactive
  Clear and concise
EVM-based checkpoint control
Risk management
  Especially along the critical path
Delegation
Contracts!
  Transfer and mitigate risk

## Slide 231
Week 13
Agile and Extreme Project Management

## Slide 232: Lesson Overview
Agile and Extreme Project Management
Reading: Chapter 10 and 11
Objectives
  Distinguish agile and extreme projects from traditional projects
  Analyze the unique challenges of projects of these types and discuss ways to successfully overcome them

## Slide 233
Agile and Extreme Project Management

## Slide 234: Non-traditional Projects
Agile projects
  Goal is clearly understood
  Exact solution is not at all clear
  Periodic releases of working systems
Extreme projects
  Goal is idealistic
  Solution is unknown or unrealistic
  Do a little work, learn and evaluate
  Project may end after any phase

## Slide 235: Agile Project Management
The Agile Manifesto (Fowler and Highsmith)
  Individuals and interactions over processes and tools
  Working products over comprehensive documentation
  Customer collaboration over contract negotiations
  Responding to change over following a plan
Surface frequently
  Co-located, small, agile project teams
  Cross project dependencies
  Partial solutions made visible periodically

## Slide 236: The Iterative Model
Iteration is used to explore, discover and learn while moving toward an acceptable level of completion
Iterations produce increasingly complete prototypes to facilitate discovery of the complete solution
Scope can be “refined” between each iteration

## Slide 237: The Iterative Model Evaluated
Strengths
  Frequent opportunities for client review
  Facilitates continual deepening of understanding of problem and solution
  Suggested improvements vs. scope creep
  Overall plan can be adapted with changing environment (e.g., market, technology, etc.)
Weaknesses
  Client can be too involved
  Co-location may be impractical
  Supporting interim “solutions” may be burdensome
  Number of iterations required to “finish” is not known

## Slide 238: The Adaptive Model
The future is less certain
Knowledge gained in one iteration will be used to direct the next iteration
  Just-in-time planning
The goal is convergence toward an acceptable solution
  High-risk, high-reward?
Partial solutions may be released at the discretion of the client

## Slide 239: The Adaptive Model Evaluated
Strengths
  Very focused, only essential work is performed
  Minimal change management overhead
  Minimal uncertainty management
  Frequent production of business value
Weaknesses
  Only works with significant, timely, meaningful client involvement
  Commitment to more meaningful deliverables is all but impossible

## Slide 240: Extreme Project Management
Rapid and very visible progress toward a yet to be determined solution to a vague and evolving problem
Capability and desire in search of a solution which in turn will search for a problem
Change is a given since the next iteration is at best loosely defined until the current iteration is assessed
Success must be thought of in different terms – knowledge gained

## Slide 241: Extreme PM Evaluated
Strengths
  Extremely engaging (creative problem solving)
  Extremely flexible
  Rapid breezing over of many possible solutions
  Facilitates getting “out of the box”
Weaknesses
  Commitment to anything but exploration is futile
  Encourages play, not work
  Drives sales and marketing crazy
  Who’s paying for this?

## Slide 242
Week 14
Enterprise Project Management

## Slide 243: Sim Project Assessment Details
Append 2 pages to your plan document
Page 1 - EVM and supporting metrics
  A single EVM graph (original PV line plus EV and AC lines)
  1 table of data (duration and cost at each milestone)
  1 table of metrics (SV, CV, SPI, and CPI at each milestone)
Page 2 - Analysis
  Explain the results of each milestone
  Explain improvements you would make next time
Appendix
  Include a picture of your masterpiece
Submit by 12/1/14

## Slide 244: Lesson Overview
Enterprise Project Management
Reading: Chapter 18
Objectives
  Define the concept of enterprise organizations
  Explore project management at the enterprise level
  Discuss the business climate and how enterprise project management addresses strategy
  Examine the process flow of enterprise project management

## Slide 245
Enterprise Project Management

## Slide 246: The Enterprise
Spanning the organization
  Work flows through an organization being processed at “stations” like an assembly line
Business units and administrative functions coordinating efforts to realize strategic goals
  “Silos” of commonality (development, sales, HR, manufacturing, etc.)
  Organized to manage long-term command and control
Portfolios of projects
  Logically related tactical projects defined to address strategic goals

## Slide 247: A View from the Top

## Slide 248: Enterprise Project Management
Start with the end in mind
  Identify the big deliverable
  Break it down into phased deliverables
Manage as a collective
  All phases must be completed to successfully complete the portfolio
  Each phase is a project
  Learn as you go, refine plans as necessary
Portfolio perspectives
  Progressing toward the strategy’s finish line
  A dedicated, finite set of resources

## Slide 249: Enterprise PM Process Flow
COLLECT ideas
ANALYZE the ideas to develop a set of tactics
SELECT tactics based on selection criteria
INITIATE by developing plans
EXECUTE the plans and monitor progress
DEPLOY deliverables and support compliance