## Sheet1
Task(s)
Start Date End Date |  | Description | Duration(days)
2014-10-26 | 2014-11-01 | Create plan | 7
2014-11-08 | 2014-11-08 | Invite Guests via Emails | 1
2014-11-08 | 2014-11-21 | Receive RSVPs | 14
2014-11-22 | 2014-11-22 | Shop | 1
2014-11-23 | 2014-11-25 | Thaw Turkey | 3
2014-11-26 | 2014-11-26 | Brine Lamb | 1
2014-11-26 | 2014-11-26 | Brine Turkey | 1
2014-11-26 | 2014-11-26 | Immerse Red Bean | 1
2014-11-26 | 2014-11-26 | Shop (flower and fish) | 1
2014-11-27 | 2014-11-27 | Dinner Party (including preparation) | 1
2014-11-28 | 2014-11-28 | Cleanup After Party | 1
Task(s) 11/27/2014
Start Time End Time |  | Description | Duration(hours)
8:00 | 8:30 | Clean Turkey | 0.5
8:30 | 9:00 | Stuff Turkey | 0.5
9:00 | 16:00 | Cook Turkey | 7
16:00 | 17:00 | Cool / sice Turkey | 1
9:00 | 11:00 | Clean house | 2
13:00 | 14:00 | Cook red bean | 1
14:00 | 16:00 | Immerse agaric | 2
14:00 | 15:00 | Setup table | 1
15:00 | 16:00 | Decorate | 1
16:00 | 16:30 | Prepare plates | 0.5
16:00 | 16:30 | Cook tilapia | 0.5
16:30 | 17:00 | Warm tilapia | 0.5
16:30 | 17:00 | Cook lamb | 0.5

## Sheet2
ID | Activity | Immediate Predecessor(s) | Duration (hour) | Budget (dollar)
1 | Create Plan | - | 8 | 0
2 | Invite Guests via Email | 1 | 1 | 0
3 | Receive RSVPs | 2 | 2 | 0
4 | Shop | 3 | 4 | 120
5 | Thaw Turkey | 4 | 36 | 0
6 | Brine Turkey | 5 | 12 | 0
7 | Stuff Turkey | 6 | 0.5 | 0
8 | Cook Turkey | 7 | 7 | 0
9 | Cool / Slice Turkey | 8 | 1 | 0
10 | Brine Lamb | 3 | 12 | 0
11 | Cook Lamb | 10 | 0.5 | 0
12 | Immerse Red Bean | 3 | 12 | 0
13 | Cook Red Bean | 12 | 1 | 0
14 | Ground Red Bean | 13 | 0.5 | 0
15 | Cook Red Bean with Milk Soup | 14 | 0.2 | 0
16 | Cook Tilapia | 3 | 0.5 | 0
17 | Cook Soup | 3 | 8 | 0
18 | Immerse Agaric | 3 | 1 | 0
19 | Cook Green Chinese cabbage with agaric | 18 | 0.1 | 0
20 | Cook Potherb mustard with ground pork | 3 | 0.5 | 0
21 | Cook Rice | 3 | 0.5 | 0
22 | Heat water for Tea | 3 | 0.5 | 0
23 | Clean House | 7 | 2 | 0
110.8